## 20%IRA
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1st QUARTER, CY 2015
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks (Date of Obligation)
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Repair/improvement of Farmer's Pavillion (Phase II) | Sta. Barbara, Pangasinan | 2973554 | Bid 3/5/2015 - 3/15/2015 |  | 87% |  |  | 1/28/2015 | 6911 | PR# 0082
Proposed Perimeter Fence | Ketegan E/S., Brgy. Ketegan, Bautista, Pangasinan | 1405947 | Not Yet Starter |  |  |  |  | 2015-03-04 | 6911 | PR# 1202
Construction of Slope Protection | along Calarian Creek, Nursery, Tebag, Sta. Barbara, Pangasinan | 1446450 | 2014-10-08 |  | 48% |  |  | 2015-03-04 | 6911 | PR#0614
2-Storey Multi-purpose Bldg. (ABC Building) Phase II, | Alvear Street, Lingayen, Pangasinan | 1861017 | Bid 4/21/2015-5/2/2015 |  | On Going |  |  | 2015-03-04 | 6911 | PR#0312
Construction of 1 unit 2-Storey Multi-Purpose Bldg., (Brgy. Hall), | Poblacion East, Bautista, Pangasinan | 2305855 | [5 empty] | 2015-03-04 | 6911 | PR#0763
Additional works of various of various buildings at EPDH, | Tayug, Pangasinan | 2238748 | 2014-01-06 | 2015-04-20 | 100% |  |  | 2015-03-04 | 6911 | PR#0059
Renovation/Improvement of Pangasinan Internal Affair Service (PIAS) Building, PNP Headquarters, | Lingayen, Pangasinan | 1146662 | 2015-02-02 | 2015-04-25 | 100% |  |  | 2015-03-04 | 6911 | PR#1237
installation of Reinforced Concrete Culvert Pipes (RCCP)), Nursery Compound, | Tebag, Sta. Barbara, Pangasinan | 217442 | Not Yet Starter |  |  |  |  | 2015-03-04 | 6911 | PR#0378
Improvement of CT Scan Room | Pangasinan Provincial Hospital | 388107 | [5 empty] | 2015-03-04 | 6911 | PR#0630
Rehabilitation/Concreting of Basement flooring of Malong and Palaris Buildings, Capitol Compound, | Lingayen, Pangasinan | 221234 | Not Yet Starter |  |  |  |  | 2015-03-04 | 6911 | PR#1187
construction of Philippine Affairs Office (Pangasinan Chapter), Capitol Compound, | Lingayen, Pangasinan | 1979401 | 2014-12-03 | 2015-01-08 | 100% |  |  | 2015-03-12 | 6911 | PR#2456
Repair/Rehab of Repair Bay 1 and Office Building, Motorpool Compound, | Lingayen, Pangasinan | 2593367 | 2014-06-05 | 2015-01-03 | 100% | 2593367 |  | 2015-03-12 | 6911 | PR#1916
396 MT Asphalt Pre-mix and 17 drums Emulsified Asphalt for the improvement of Road Network and Parking Area @ Bayambang Dist. Hospital, | Bayambang, Pangasinan | 2422800 | 2014-12-11 | 2015-12-13 | 100% | 2443024.92 |  | 2015-03-23 | 6911 | PR#2621
construction of Multi-Purpose Bldg., (Brgy. Hall), | Brgy Mapolopolo, Basista, Pangasinan | [6 empty] | 2015-03-23 | 6911 | PR#1319
construction of Stone Masonry with Barriers along Mabilao-Binday Prov'l Road, | San Fabian, Pangasinan | 555185 | 2014-10-07 | 2015-01-23 | 100% |  |  | 2015-01-28 | 8917-1 | PR#0211
repainting of various concrete bridges | 1st-6th Pangasinan Engineering Districts | 266039 | 2014-01-19 | 2014-12-05 | 100% |  |  | 2015-02-27 | 8917-1 | PR#1204
construction of Stone masonry with barrier and concreting of Road Shoulder along Mabilao-Binday Road, | San Fabian, Pangasinan | 1371178 | 2014-09-22 | 2014-12-12 | 100% |  |  | 2015-03-04 | 8917-1 | PR#1034
repainting of various Provicial Steel Bridges | around the Province of Pangasinan | 190261 | 2014-02-25 | 2014-04-28 | 100% |  |  | 2015-03-23 | 8917-1 | PR#1142
Mr. Bernabe Cabrera Salayog- Financial Assistance, cost of tiling works of Sodality Road | Manaoag, Pangasinan | 500000 | [5 empty] | Paid Jan., 2015
repair of Sison Auditorium (Vice-Governor's Room), | Lingayen, Pangasinan | 187485 | [5 empty] | 2015-02-11 | 3917 | PR#0311
furnishing materials, labor, equipment and others- for the completion of 2-storey Multi-Purpose building (Brgy. Hall), | San Guillermo, San Jacinto, Pangasinan | 1397805 | [5 empty] | 2015-03-19 | 3917 | PR#2921
Economic Development
Asphalting and blocktopping of RHU and Municipal Hall Compound, | Urbiztondo, Pangasinan | 1505900 | 2015-02-13 | 2015-02-26 | 100% | 1684616 |  | 2015-03-04 | 6911 | PR#0036
Asphalting of Victorio-Pangascasan (Sual Coastal Road), Victoria Sec., | Alaminos City | 644000 | 2014-09-30 | 2014-10-14 | 100% | 908956.24 |  | 2015-01-28 | 8917-1 | PR#0157
concreting of Brgy. Esperanza Road, | Sison, Pangasinan | 158774 | [5 empty] | 2015-02-11 | 8917-1 | PR#0253
Asphalting of Frank's Canteen Compound, | Lingayen, Pangasinan | 314800 | 2015-03-25 | 2015-03-25 | 100% | 347759.07 |  | 2015-02-11 | 8917-1 | PR#0212
Asphalt materials for the Proposed Blocktopping of Brgy. Buenlag Road, | Bugallon, Pangasinan | 4058900 | Materials Only |  |  |  |  | 2015-03-04 | 8917-1 | PR#0060
blocktopping of Cervantes Road, | Brgy. Salomague Norte, Bugallon, Pangasinan | 648200 | Not Yet Starter |  |  |  |  | 2015-03-04 | 8917-1 | PR#0212
414 MT Asphalt Pre-Mix and 18 drums Emulsified Asphalt in Asphalting of Balangobong Road, | Alaminos, Pangasinan | 2536200 | 2015-01-19 | 2015-01-22 | 100% | 2700255.78 |  | 2015-03-04 | 8917-1 | PR#1223
concreting and construction of slope protection (stone masonry) | Brgy. Poponto, Bautista, Pangasinan | 4175839 | Bidded 4/21/2015 |  |  |  |  | 2015-03-04 | 8917-1 | PR#0754
construction of stone masonry | Brgy. Macalong, Asingan, Pangasinan | 3652065 | Not Yet Starter |  |  |  |  | 2015-03-04 | 8917-1 | PR#0398
concreting of Tombor Road, Phase II, | Binmaley, Pangasinan | 1794383 | Bid- 4/21/2015 |  |  |  |  | 2015-03-04 | 8917-1 | PR#0691
blocktopping/patching of various Poblacion Roads | Manaoag, Pangasinan | 925800 | 2015-02-02 | 2015-02-03 | 100% | 970697 |  | 2015-03-04 | 8917-1 | PR#0631
asphalting of By-pass Road, Poblacion, | Manaoag, Pangasinan | 340200 | 2015-02-10 | 2015-02-10 | 100% | 338072.55 |  | 2015-03-16 | 8917-1 | PR#2106
259 MT Asphalt in Asphalting of Pinmilapil Road | Sison, Pangasinan | 1582900 | 2015-03-05 | 2015-03-10 | 100% | 1423049.63 |  | 2015-03-16 | 8917-1 | PR#1879
Asphalting of Amagbagan Road, | Sison, Pangasinan | 1972600 | 2015-02-10 | 2015-02-18 | 100% | 2046210.16 |  | 2015-03-16 | 8917-1 | PR#1917
Asphalting of Poblacion road | Dama de Noche St. and Cemetery road, Mapandan, Pangasinan | 563600 | 2014-10-22 | 2014-10-22 | 100% | 580059.44 |  | 2015-03-16 | 8917-1 | PR#2184
Asphalting of Brgy. Macalong Road, | Asingan, Pangasinan | 861900 | 2014-12-04 | 2014-12-05 | 100% | 909729.74 |  | 2015-03-23 | 8917-1 | PR#1796
asphalting of Pantal Road, | Bugallon, Pangasinan | 2597500 | 2012-12-08 | 2013-01-04 | 100% | 2680239 |  | 2015-03-23 | 8917-1 | PR#2261
Asphalting of various streets | Bayambang, Pangasinan | 4755300 | 2015-03-12 | 2015-03-21 | 100% | 5819274.6 |  | 2015-03-23 | 8917-1 | PR#2807
Asphalting various streets at | Bayambang, Pangasinan | 3591400 | 2013-03-21 | 2013-04-23 | 100% | 3992324.5 |  | 2015-03-23 | 8917-1 | PR#2730
construction of slope protection (Gabions) of the eroded riverbank along Shahani Road, | Brgy. Toboy, Asingan, Pangasinan | 4076795 | Not Yet Starter |  |  |  |  | 2015-04-10 | 8917-1 | PR#0903
Proposed Concrete paving along San Jacinto-Pozorrubio Road, Lobong Section, | San Jacinto, Pangasinan | 2692805 | Not Yet Starter |  |  |  |  | 2015-04-10 | 8917-1 | PR#0693
concreting of Sitio Cupang Road, | Brgy. Umanday, Bugallon, Pangasinan | 545054 | 2014-05-05 | 2014-07-09 | 100% | 3060044 |  | 2015-03-19 | 3917 | PR#0704
100 units diesel engine water pump with complete accessories |  | 2400000
Loans Granted to various Multi-Purpose Cooperatives and Associations |  | 1000000 | N/A | N/A |  |  |  |  | 8915
Tools needed for 2 drilling Team @ Waterworks Section, | PEO, Lingayen, Pangasinan | 173570.78 | Materials Only |  |  |  |  | 2015-02-25 | 8919-2 | PR#0632
construction of 1 unit Deepwell Handpump at | Nalsian - Bacayao, Calasiao, Pangasinan | 113118 | 2014-10-15 | 2014-10-29 | 100% |  |  | 2015-03-09 | 8919-2 | PR#0247
construction of one unit Artesian Well at | Brgy. Leet, Sta. Barbara, Pangasinan | 139921 | Not Yet Starter |  |  |  |  | 2015-03-09 |  | PR#0379
Environmental Development
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO | [5 empty] | AMADO T. ESPINO, JR.
Provincial Accountant | [5 empty] | Governor

## LDRR.UTILIZATION REPORT
FDP Form 8 - Local Disaster Risk Reduction and Management Fund Utilization
(COA Form)
LOCAL DISASTER RISK REDUCTION AND MANAGEMENT FUND UTILIZATION
For the Quarter JANUARY - MARCH , CY 2015
Province of Pangasinan
LDRRMF
Particulars | Quick Response | Mitigation Fund | NDRRMF | From Other LGUs | From Other Sources | Total
| Fund (QRF) | 70%
30%
A. Sources of Funds:
Current Appropriation | 0 | 34238473.5 |  |  |  | 34238473.5
Continuing Appropriation | [5 empty] | 0
Previous Year's Appropriation transferred to the Special Trust Fund |  | 45024785.74 |  |  |  | 45024785.74
Transfers/Grants | [5 empty] | 0
Others ( Please specify) | [5 empty] | 0
Total Funds Available | 0 | 79263259.24 | 0 | 0 | 0 | 79263259.24
B. Utilization
Medicines | [5 empty] | 0
Medical Supplies | [5 empty] | 0
Food Supplies | [5 empty] | 0
Office Supplies |  | 60550 |  |  |  | 60550
Repair of Evacuation Center | [5 empty] | 0
Institutional/Capacity Development ( Ex. Trainings, environmental assessment & other related activities) | [5 empty] | 0
Construction of Evacuation Center | [5 empty] | 0
Equipment | [5 empty] | 0
Transfer to other LGUs | [5 empty] | 0
Other Maintenance and Operating Expenses |  | 5602270 |  |  |  | 5602270
Traveling Expense |  | 64010.28 |  |  |  | 64010.28
Training Expense | [5 empty] | 0
IT Equipment & Software | [5 empty] | 0
Motor Vehicles | [5 empty] | 0
Other Machineries and Equipment |  | 1741000 |  |  |  | 1741000
Watercrafts |  | 4663000
Other Property, Plant and Equipment | [5 empty] | 0
Roads, Highways and Bridges | [5 empty] | 0
Communication Equipment | [5 empty] | 0
Gasoline, Oil, Lubricants | [5 empty] | 0
Donations | [5 empty] | 0
Repair/Rehabilitation of Public Infrastructures, Roads, Highways and Bridges, etc. | [5 empty] | 0
Repair & Maintenance-Motor Vehicles |  | 17400 |  |  |  | 17400
Total Utilization | 0 | 12148230.28 | 0 | 0 | 0 | 12148230.28
Unutilized Balance | 0 | 67115028.96 | 0 | 0 | 0 | 67115028.96
I hereby certify that I have reviewed the contents and hereby attest to the veracity and correctness of the data or
information containedin this document.
ARTURO V. SORIANO
Provincial Accountant

## SEF
FDP Form 11 - SEF Utilization
(SEF Budget Accountability Form No. 1)
REPORT OF SEF UTILIZATION
For the Quarter Ending March 31, 2015
Province/City Municipality |  | Pangasinan
Receipt from SEF |  |  |  | 76430522.26
Less: | DISBURSEMENTS (broken down by expense class and by object of expenditure)
Personal Services
-0-
Maintenance and Other Operating Expenses
24206169
Capital Outlay
-0-
Financial Expenses
-0-
Sub-total |  |  |  | 24206169
Balance |  |  |  | 52224353.26
We hereby certify that we have reviewed the
contents and hereby attest to the veracity and
correctness of the data or information
contained in this document.
ARTURO V. SORIANO
Provincial Accountant
AMADO T. ESPINO, JR.
Governor

## CASHFLOWS
FDP Form 9 - Statement of Cash Flow
(COA Form)
Province of Pangasinan
STATEMENT OF CASH FLOWS
General Fund
For the First Quarter Ending March 31, 2015
Cash Flows from Operating Activities:
Cash Inflows:
|  | Collection from Taxpayers | 141603506.71
|  | Share from Internal Revenue Collections | 607436973
|  | Receipts from sale of goods or services | 92736084.65
|  | Interest Income | 945678.78
|  | Other Receipts | 106132119.21
|  | Total Cash Inflow | 948854362.35
Cash Outflows:
Payments to -
|  | To suppliers/creditors | 488684139.07
|  | To employees | 232466947.64
|  | Interest Expenses | 9371236.63
|  | Other Disbursements | 2132
|  | Total Cash Outflow | 730524455.34
| Cash Provided by (Used In) |  |  | 218329907.01
Cash Flows from Investing Activities:
Cash Inflows:
Sale of Property, Plant and Equipment and Public
Infrastracture
Sale of Debt Securities of other Entities
|  | Collection of Principal on Loans to other Entities | 2089210
|  | Total Cash Inflow | 2089210
Cash Outflows:
|  | Purchase of Property, Plant and Equipment and Public | 87992913.35
Infrastracture
Grant/Loans to Other Entities
|  | Total Cash Outflow | 87992913.35
| Cash Provided by (Used In) |  |  | -85903703.35
Cash Flows from Financing Activities:
Cash Inflows:
Issuance of Debt Securities
|  | Acquisition of Loan | 424268
|  | Total Cash Inflow | 424268
Cash Outflows:
Retirement/.Redemption of Debt Securities
|  | Payment of Loan Amortization | 24693802.93
|  | Total Cash Outflow | 24693802.93
| Cash Provided by (Used In) |  |  | -24269534.93
Net Increase in Cash |  |  |  | 108156668.73
Cash at Beginning of the Period |  |  |  | 642093085.7
Cash at the End of the Period |  |  |  | 750249754.43
Certified Correct:
ARTURO V. SORIANO, CPA
Provincial Accountant

## TRUST FUND UTILIZATION
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE JANUARY - MARCH QUARTER, CY 2015
Province: PANGASINAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA
Provincial Accountant
AMADO T. ESPINO, JR.
Governor
NONE

## UNLIQUIDATED
FDP Form 12- Unliquidated Cash Advances
UNLIQUIDATED CASH ADVANCES
As of March 31, 2015
Province, City or Municipality:
Name of Debtor (in alphabetical order) | Amount Balance | Date Granted | Purpose | Amount Due
|  |  |  | Current |  |  | Past Due
|  |  |  | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
Rommel Cardinoza | 0 | 2014-01-16
Cornel V. dela Cruz | 0 | 2014-01-16
Gerardo R. Santos | 0 | 2014-01-09
Aurora L. Bacay | 0 | 2014-01-09
Edwin B. Sison | 0 | 2014-01-08
Salvador Vedaña | 10000 | 2003-10-08 | Traveling Expenses | [5 empty] | 10000
Judge Dionisio C. Sison | 7000 | 2001-07-16 | [6 empty] | 7000
Eugenio G. Ramos | 2500 | 1999-04-14 | [6 empty] | 2500
Atty. Feliciano M. Bautista | 1200 | 1997-07-22 | Traveling Expenses | [5 empty] | 1200
BM Eduardo Perez, Sr. | 5000 | 1999-02-03 | Traveling Expenses | [5 empty] | 5000
BM Leonardo Caranto | 20000 | 1997-02-27 | Traveling Expenses | [5 empty] | 20000
BM Rogelio Law | 5000 | 1997-09-22 | Traveling Expenses | [5 empty] | 5000
Rodolfo M. Cortez | 20000 | 1996-06-20 | [6 empty] | 20000
Rodolfo M. Cortez | 30000 | 1997-04-10 | [6 empty] | 30000
Roderick Mina | 3600 | 1997-06-22 | Traveling Expenses | [5 empty] | 3600
Felipe Santillan | 1250 | 1978-02-28 | Traveling Expenses | [5 empty] | 1250
Narciso Ramos | 1250 | 1978-08-28 | Traveling Expenses | [5 empty] | 1250
Rodolfo Rodrigo | 500 | 1978-11-23 | Traveling Expenses | [5 empty] | 500
Rodolfo Itchon | 1000 | 1981-03-19 | Traveling Expenses | [5 empty] | 1000
Rodolfo Itchon | 1500 | 1982-05-07 | Traveling Expenses | [5 empty] | 1500
Rodolfo Rivera | 1300 | 1983-06-04 | Traveling Expenses | [5 empty] | 1300
Federico Victorio | 1500 | 1985-04-30 | Traveling Expenses | [5 empty] | 1500
Maximu Dulay | 5000 | 1989-06-16 | [6 empty] | 5000
Total | 117600 |  |  | 0 | 0 | 0 | 0 | 0 | 117600
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO |  |  |  |  | AMADO T. ESPINO, JR
Provincial Accountant |  |  |  |  | Governor