## 20%IRA
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1st QUARTER, CY 2016
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks (Date of Obligation)
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Construction of Senior Citizen Bldg., | Brgy. Buenlag, Calasiao | 1001591 |  |  |  | 1001591 |  | Obligated | PR#0120 | 6911
Completion/expansion of covered court at | Brgy. Quibaol, Lingayen | 1600000 |  |  |  | 1600000 |  | Obligated | PR#100 | 6911
Completion of covered court at | Libsong East, Lingayen | 1800000 | 2016-02-25 | On-going | 30% | 1800000 |  | Obligated | PR#100 | 6911
Construction of Multi-purpose bldg. | Brgy. Mancup, Calasiao, Pangasinan | 2307661 |  |  |  | 1001591 |  | Obligated | PR#0150 | 6911
Construction of Solar Dryer, | Brgy. Carayacan, San Quintin, Pangasinan | 1050899 |  |  |  | 1600000 |  | Obligated | PR#0030 | 6911
Construction of covered court (gymnsium) | Umanday C/S, Bugallon | 2473530 |  |  |  | 2473530 |  | Obligated | PR#0390 | 6911
Construction of covered court (gymnsium) | Polong, Bugallon | 2473530 |  |  |  | 2473530 |  | Obligated | PR#0587 | 6911
Construction of covered court (gymnsium) | Torres Bugallon E/S, Bugallon | 2473530 |  |  |  | 2473530 |  | Obligated | PR#0645 | 6911
Construction of covered court (gymnsium) | Brgy. Salomague Sur, Bugallon | 2473530 | 2016-03-01 | On-going | 10% | 2473530 |  | Obligated | PR#0494 | 6911
Construction of covered court (gymnsium) | Brgy. Bacabac, Bugallon | 2473530 |  |  |  | 2473530 |  | Obligated | PR#0549 | 6911
Construction of covered court (gymnsium) | Brgy. Bolaoen, Bugallon | 2473530 |  |  |  | 2473530 |  | Obligated | PR#0352 | 6911
Construction of covered court (gymnsium) | Brgy. Buenlag, Bugallon | 2473530 |  |  |  | 2473530 |  | Obligated | PR#0278 | 6911
Repair/improvement of MP Court (concreting of flooring) at Canarvacanan Cent. Sch and roofing works for stage at Canarvacanan Nat'l High School, | Alcala, Pangasinan | 368784 |  |  |  | 368784 |  | Obligated | PR#1817 | 6911
Construction of standard 1 unit 3 classroom School Building at Pindangan Elem. Sch., | Sison, Pangasinan | 2430000 |  |  |  | 2430000 |  | Obligated | PR#1789 | 6911
Construction of drainage canal w/ cover and storm drainage at | Brgy. San Miguel, Calasiao | 499086 |  |  |  | 499086 |  | Obligated | PR#2093 | 6911
Construction of covered court (gymnasium) at Pangasinan (Evacuation Center w/ CR and railings | Brgy. Cayanga, Bugallon, | 2700000 |  |  |  | 2700000 |  | Obligated | PR#2234 | 6911
Construction of Tribal hall, | Brgy. San Jose, Labrador | 499980 |  |  |  | 499980 |  | Obligated | PR#2669 | 6911
90 MT Asphalt pre-mix in asphalting | Curareng Road, Alcala, Pangasinan | 495000 | Materials Only |  |  | 495000 |  | Obligated | PR#2236 | 6911
Repair of roofing and painting of ceiling of Prov'l Jail | Lingayen, Pangasinan | 125849 | 2016-02-02 | 2016-03-15 | 100% | 125849 |  | Obligated | PR#2841 | 6911
Repair/rehabilitation of Muliti-purpose Basketball court | Asan sur, Sison, Pangasinan | 435675 |  |  |  | 435675 |  | Obligated | PR#3009 | 6911
Repair of ceiling of PSWDO (Bahay Pag-asa), Lingayen | Lingayen, Pangasinan | 400000 |  |  |  | 400000 |  | Obligated | PR# 1291 | 3917
Construction/ installation of 18 units streetlights at Capitol beachfront | Lingayen, Pangasinan | 634431 |  |  |  | 634431 |  | Obligated | PR# 1275 | 3917
Construction of Boy Scout of the Philippines Regional Off. Bldg., | Lingayen, Pangasinan | 3500000 |  |  |  | 3500000 |  | Obligated | PR# 1276 | 3917
Rehabilitation of NRSCC Restaurant, Lingayen (part of P9,544,32.00) | Lingayen, Pangasinan | 4544632 | 2015-08-03 | On-going | Not Stated | 4544632 |  | Obligated | PR# 1277 | 3917
Upgrading/ improvement/ rehabilitation of Umingan Com. Hosp., | Umingan, Pangasinan | 229520.57 |  |  |  | 229520.57 |  | Obligated | PR#0378 | 3917
Construction of perimeter fence at Artacho E/S , | Bautista, Pangasinan | 774046 |  |  |  | 774046 |  | Obligated | PR#3317 | 3917
Improvement/painting of perimeter fence and concrete pavement of basketball court | Poponto, Bautista, Pangasinan | 925743 |  |  |  | 925743 |  | Obligated | PR#3313 | 3917
Labor, materials, equipment and other incidentals for the construction of Multi-purpose covered court at Casloscaoayan, NH/S, | Bautista, Pangasinan | 1698187 | Labor and Materials Only |  |  | 1698187 |  | Obligated | PR#3318 | 3917
Construction of additional one well source w/ motorpump and tank, Manaoag Com. Hosp., | Manaoag, Pangasinan | 227300 |  |  |  | 227300 |  | Obligated | PR#3668 | 3917
TOTAL |  | 45563094.57 |  |  |  | 44806125.57
Economic Development
Loans granted to various Associations and Multi-Purpose Cooperatives |  | 2310000 | Loans Only |  |  | 2310000 |  | Obligated
Amortization of Principal and Interest on Loan to the LBP |  | 25903487.92 | Loans Only |  |  | 25903487.92 |  | Obligated
670 MT Asphalt Pre-mix for the asphalting of Amandiego Road, | Alaminos City | 3685000 | Materials Only |  |  | 3685000 |  | Obligated | PR#0120 | 6911
233 MT Asphalt Pre-mix, 7 drums E. Asphalt for patching/blocktopping of Inmalog Sur Road, | San Fabian, Pangasinan | 1382300 | Materials Only |  |  | 1382300 |  | Obligated | PR#0133 | 6911
339 MT Asphalt Pre-mix for the Asphalting of Palamis Road, | Alaminos City | 1864500 | Materials Only |  |  | 1864500 |  | Obligated | PR#0109 | 6911
285 MT Asphalt Pre-mix and 12 drums Emulsified asphalt for the asphalting of Brgy. Carot Road, | Anda, Pangasinan | 1740300 | Materials Only |  |  | 1740300 |  | Obligated | PR#0084 | 6911
19 drums Emulsified Asphalt and 619 MT Asphalt Pre-mix for the blocktopping of various Municipal Streets | Bautista, Pangasinan | 3678100 | Materials Only |  |  | 3678100 |  | Obligated | PR#0086 | 6911
8 drums Emulsified Asphalt and 181 MT Asphalt Pre-mix for the proposed asphalting of Brgy. Linoc Road, | Binmaley, Pangasinan | 1110700 | Materials Only |  |  | 1110700 |  | Obligated | PR#0026 | 6911
7 drums emulsified Asphalt and 246 MT Asphalt Pre-mix for use in the blocktopping of Papagueyan Road | Binmaley, Pangasinan | 1453800 | Materials Only |  |  | 1453800 |  | Obligated | PR#0051 | 6911
736 MT Asphalt Pre-mix and 23 drums Emulsified Asphalt for the asphalting of Basing Road | Binmaley, Pangasinan | 4379200 | Materials Only |  |  | 4379200 |  | Obligated | PR#0083 | 6911
138 MT Asphalt Pre-mix and 4 drums Emulsified Asphalt for the blocktopping of Brgy. Domalandan West Road | Lingayen, Pangasinan | 816600 | Materials Only |  |  | 816600 |  | Obligated | PR#0079 | 6911
218 MT Asphalt Pre-mix and 10 drums Emulsified Asphalt for the asphalting of Sitio Pandel and Sitio Dr. De Vera Road, Brgy. Domalandan Center | Lingayen, Pangasinan | 1343000 | Materials Only |  |  | 1343000 |  | Obligated | PR#0052 | 6911
Asphalt materials for the blocktopping of Brgy. Macarang Road | Mangatarem, Pangasinan | 3205900 | Materials Only |  |  | 3205900 |  | Obligated | PR#0019 | 6911
Concreting along Sitio Casilagan Road, Brgy. | San Juan, San Manuel, Pangasinan | 1073239 |  |  |  | 1073239 |  | Obligated | PR#1766 | 6911
Concreting of Anonang Farm to Market (FMR), Pangasinan (with slope protection) | Brgy. Anonang, San Fabian | 1505227 |  |  |  | 1505227 |  | Obligated | PR#1806 | 6911
Rehabilitation of Lumbang Bridge, | Calasiao, Pangasinan | 3820595 |  |  |  | 3820595 |  | Obligated | PR# 1292 | 3917
Jetmatic pumps and G.I. Pipes (part of P 4,417,700.00) | Province of Pangasinan | 1600000 | Materials Only |  |  | 1600000 |  | Obligated | PR#0378 | 3917
Jetmatic pumps and G.I. Pipes (part of P 4,417,700.00) | Province of Pangasinan | 2817700 | Materials Only |  |  | 2817700 |  | Obligated | PR#0378 | 8919-2
312 MT Asphalt Pre-mix and 14 drums E. Asphalt -blocktopping of Villa Road, Brgy. Villanueva and Primicias | Bautista, Pangasinan | 1917600 | Materials Only |  |  | 1917600 |  | Obligated | PR#3314 | 3917
647 MT Asphalt Pre-mix and 20 drums E. Asphalt - blocktopping of Puelay-Amanperez Prov'l Road, | Villasis, Pangasinan | 3846500 | Materials Only |  |  | 3846500 |  | Obligated | PR#3315 | 3917
502 MT Asphalt pre-mix and 15 drums E. asphalt - blocktopping of Unzad Road | Villasis, Pangasinan | 2977000 | Materials Only |  |  | 2977000 |  | Obligated | PR#3316 | 3917
Construction of sideslope protection along San Jacinto - Pozorrubio Road, | Pozorrubio, Pangasinan | 2000000 |  |  |  | 2000000 |  | Obligated | PR#3008 | 3917
Widening of the road going to Palapad Seminary, | San Fabian, Pangasinan | 5868850 | 2016-02-24 | On-going | 35% | 5859959 |  | Obligated | Alcel Constn PR#0078 | 8917-1
Concreting of San Manuel - San Nicolas Rd., | San Nicolas, Pangasinan | 1163000 |  |  |  | 1163000 |  | Obligated | PR#0036 | 8917-1
Concreting of parking area of the Los Caballeros Club | Bgry. Pob. Manaoag, Pangasinan | 1508582 |  |  |  | 1508582 |  | Obligated | PR#0056 | 8917-1
Concreting of Inmanduyan Rd. | Laoac, Pangasinan | 1394995 |  |  |  | 1394995 |  | Obligated | Lucky G18 PR#0032 | 8917-1
Concreting of Macabito Barangay Rd. | Calasiao, Pangasinan | 2996589 | 2016-01-25 | On-going | Not Stated | 2996589 |  | Obligated | PR#0076 | 8917-1
Concreting of San Aurelio 3rd FMR, | Balungao, Pangasinan | 2769900 |  |  |  | 2769900 |  | Obligated | PR#0057 | 8917-1
Concreting of Polong West Rd. (Polong South Bd. Rd.) | Bugallon, Pangasinan | 2922000 |  |  |  | 2922000 |  | Obligated | PR#0077 | 8917-1
Concreting of Purok I Centro Rd. | Brgy. Barlo, Mabini, Pangasinan | 1413467 | 2016-02-26 | Not Stated | 100% | 1413467 |  | Obligated | PR#0055 | 8917-1
Concreting of Buer, Brgy. Rd. | Aguilar, Pangasinan | 1440000 |  |  |  | 1440000 |  | Obligated | PR#0037 | 8917-1
Concreting of Brgy. Casanfernanduan Rd. | Pozorrubio, Pangasinan | 2603811 |  |  |  | 2603811 |  | Obligated | PR#0141 | 8917-1
Concreting of Brgy. Don Benito Rd. | Pozorrubio, Pangasinan | 2498295 |  |  |  | 2498295 |  | Obligated | PR#0132 | 8917-1
Concreting of Libsong East Rd. | Lingayen, Pangasinan | 2263038 |  |  |  | 2263038 |  | Obligated | PR#0135 | 8917-1
690 MT asphalt pre-mix and 30 drums emulsified asphalt for the asphalting of Sta. Catalina Rd. | Binalonan, Pangasinan | 4227000 | Materials Only |  |  | 4227000 |  | Obligated | PR#0085 | 8917-1
575 MT asphalt pre-mix and 25 drums emulsified asphalt for the asphalting of Mancasuy Rd. | Binalonan, Pangasinan | 3522500 | Materials Only |  |  | 3522500 |  | Obligated | PR#0073 | 8917-1
Rehabilitation/improvement/ upgrading of Burgos-Iliw-Iliw Rd. | Burgos, Pangasinan | 11881142.96 |  |  |  | 11881142.96 |  | Obligated | Alcel Const. PR#0388 | 8917-1
Rehabilitation/improvement/ upgrading of Urbiztondo-San Carlos Rd., (part of P87,957,208.21) | Urbiztondo, Pangasian | 23536109.26 |  |  |  | 23536109.26 |  | Obligated | BET C/S PR#0476 | 8917-1
TOTAL |  | 146440028.14 |  |  |  | 146431137.14
Environmental Development
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO
Provincial Accountant
AMADO T. ESPINO, JR.
Governor

## LDRRM
FDP Form 8 - Local Disaster Risk Reduction and Management Fund Utilization
(COA Form)
LOCAL DISASTER RISK REDUCTION AND MANAGEMENT FUND UTILIZATION
For the Quarter JANUARY - MARCH , CY 2016
Province of Pangasinan
LDRRMF
Particulars | Quick Response | Mitigation Fund | NDRRMF | From Other LGUs | From Other Sources | Total
| Fund (QRF) | 70%
30%
A. Sources of Funds:
Current Appropriation | 0 | 78545600 |  |  |  | 78545600
Continuing Appropriation |  | 4390000 |  |  |  | 4390000
Previous Year's Appropriation transferred to the Special Trust Fund |  | 81556220.77 |  |  |  | 81556220.77
Transfers/Grants | [5 empty] | 0
Others ( Please specify) | [5 empty] | 0
Total Funds Available | 0 | 164491820.77 | 0 | 0 | 0 | 164491820.77
B. Utilization
Medicines | [5 empty] | 0
Medical Supplies | [5 empty] | 0
Food Supplies | [5 empty] | 0
Office Supplies | [5 empty] | 0
Repair of Evacuation Center | [5 empty] | 0
Institutional/Capacity Development ( Ex. Trainings, environmental assessment & other related activities) | [5 empty] | 0
Construction of Evacuation Center | [5 empty] | 0
Equipment | [5 empty] | 0
Transfer to other LGUs | [5 empty] | 0
Other Maintenance and Operating Expenses |  | 5142520 |  |  |  | 5142520 |  | PLUS tf
Traveling Expense | [5 empty] | 0
Training Expense | [5 empty] | 0
IT Equipment & Software | [5 empty] | 0
Motor Vehicles | [5 empty] | 0
Other Machineries and Equipment | [5 empty] | 0
Watercrafts
Other Property, Plant and Equipment |  | 1541200 |  |  |  | 1541200
Roads, Highways and Bridges | [5 empty] | 0
Communication Equipment |  | 26664000 |  |  |  | 26664000
Gasoline, Oil, Lubricants |  | 51835.98 |  |  |  | 51835.98
Donations | [5 empty] | 0
Repair/Rehabilitation of Public Infrastructures, Roads, Highways and Bridges, etc. | [5 empty] | 0
Repair & Maintenance-Motor Vehicles |  | 242175 |  |  |  | 242175
Total Utilization | 0 | 33641730.98 | 0 | 0 | 0 | 33641730.98 | 0
Unutilized Balance | 0 | 130850089.79 | 0 | 0 | 0 | 130850089.79
I hereby certify that I have reviewed the contents and hereby attest to the veracity and correctness of the data or
information containedin this document.
ARTURO V. SORIANO
Provincial Accountant

## SEF
FDP Form 11 - SEF Utilization
(SEF Budget Accountability Form No. 1)
REPORT OF SEF UTILIZATION
For the Quarter Ending March 31, 2016
Province/City Municipality |  | Pangasinan
Receipt from SEF |  |  |  | 78792817.21
Less: | DISBURSEMENTS (broken down by expense class and by object of expenditure)
Personal Services
-0-
Maintenance and Other Operating Expenses
65628233.52
Capital Outlay
Financial Expenses
-0-
Sub-total |  |  |  | 65628233.52
Balance |  |  |  | 13164583.69
We hereby certify that we have reviewed the
contents and hereby attest to the veracity and
correctness of the data or information
contained in this document.
ARTURO V. SORIANO, CPA
Provincial Accountant
AMADO T. ESPINO, JR.
Governor

## CASHFLOWS
FDP Form 9 - Statement of Cash Flow
(COA Form)
PROVINCE OF PANGASINAN
Statement of Condensed Cash Flows
GENERAL FUND
For the First Quarter Ending March 31,2016
Cash Flows from Operating Activities:
Cash Inflows:
|  | Collection from Taxpayers |  | 51083971.28
|  | Share from Internal Revenue Allotment |  | 666390858
|  | Receipts from business/service income |  | 70109703.91
|  | Interest Income |  | 681531.15
|  | Other Receipts |  | 127167394.57
|  | Total Cash Inflow |  | 915433458.91
Cash Outflows:
|  | Payment of expenses |  | 298212435.63
|  | Payment to suppliers and creditors |  | 167862806.11
|  | Payment to employees |  | 163226601.06
|  | Interest Expenses |  | 7466313.83
|  | Other Expenses |  | 40336763.02
|  | Total Cash Outflow |  | 677104919.65
| Net Cas Flows from Operating Activities |  |  | 238328539.26
Cash Flows from Investing Activities:
Cash Inflows:
|  | Proceeds from Sale of Investment Property |  | 0
|  | Proceeds from Sale/Disposal of Property, Plant and Equipment |  | 0
|  | Collection of Principal on Loans to other Entities |  | 1673050
|  | Total Cash Inflow |  | 1673050
Cash Outflows:
|  | Purchase / Construction of Investment Property |  | 0
|  | Purchase / Construction of Property, Plant and Equipment |  | 317350989.89
Purchase of Bearer Biological Assets
|  | Grant of Loans |  | 2420000
|  | Total Cash Outflow |  | 319770989.89
| Net Cash Flows from Investing Activities |  |  | -318097939.89
Cash Flows from Financing Activities:
Cash Inflows:
|  | Proceeds from Loans |  | 234222221.01
|  | Total Cash Inflow |  | 234222221.01
Cash Outflows:
|  | Payment of Long-Term Liabilities |  | 0
|  | Payment of Loan Amortization |  | 18437174.09
|  | Total Cash Outflow |  | 18437174.09
| Net Cash Flows from Financing Activities |  |  | 215785046.92
Total Cash Provided by Operating,Investing and
|  | Financing Activities |  | 136015646.29
Add:Cash at Beginning of the Quarter |  |  |  | 960665599.35
Cash at the End of the Quarter |  |  |  | 1096681245.64
Certified Correct:
ARTURO V. SORIANO, CPA
Provincial Accountant

## TRUSTFUND
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE JANUARY-MARCH QUARTER, CY 2016
Province : PANGASINAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
payment of 100% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Olo-Naguilayan Road, Mangatarem, Pangasinan | Mangatarem, Pangasinan | 4713328.82 | 2015-10-14 | 2016-01-29 | 100% | 4713328.82 |  | fund from the DPWH-SLRF
payment of 100% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Asingan-San Manuel-Agno Gorge Road, Asingan, Pangasinan | Asingan, Pangasinan | 4868678.34 | 2016-03-16 | On-going C/O PEO | 100% | 4868678.34 |  | fund from the DPWH-SLRF
payment of 100% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONSTRUCTION of Provincial Corn Farmer's Coordinating Center, Brgy. Gonzalo, San Quintin, Pangasinan (Phase I) | Brgy. Gonzalo, San Quintin, Pangasinan | 2990653.6 | 2015-11-19 | On-going C/O PEO | 100% | 2990653.6 |  | fund from the Department of Agriculture
payment of 88.60% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Pogo-Diaz Farm-to-Market Road, Bautista, Pangasinan | Bautista, Pangasinan | 1179000 | Not Stated |  | 88.60% | 1179000 |  | fund from the Department of Agriculture
payment of 87.84% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Primicias Farm-to-Market Road, Bautista, Pangasinan | Bautista, Pangasinan | 1684820.5 | Not Stated |  | 87.84% | 1684820.5 |  | fund from the Department of Agriculture
payment of various office equipment for use at Sta. Barbara Provincial Farmer's Pavilion | Sta. Barbara, Pangasinan | 1229485 | Materials Only |  |  | 1229485 |  | fund from the Department of Agriculture
payment of 100% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Farm-to-Market Road, Brgy. Guibel, San Jacinto, Pangasinan | Brgy. Guibel. San Jacinto, Pangasinan | 515408 | Not Stated | 2016-02-18 | 100% | 515408 |  | fund from the Tobacco Excise Tax
payment of 100% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Farm-to-Market Road, Brgy. Palua, Mangaldan, Pangasinan | Brgy. Palua, Mangaldan, Pangasinan | 514016 | Not Stated | 2016-02-18 | 100% | 514016 |  | fund from the Tobacco Excise Tax
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO | [5 empty] | HON. AMADO T. ESPINO, JR.
Provincial Accountant | [5 empty] | Provincial Governor

## UNLIQUIDATED.CASH.ADV.
FDP Form 12- Unliquidated Cash Advances
UNLIQUIDATED CASH ADVANCES
As of March 31, 2016
Province, City or Municipality:
Name of Debtor (in alphabetical order) | Amount Balance | Date Granted | Purpose | Amount Due
|  |  |  | Current |  |  | Past Due
|  |  |  | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
Rommel Cardinoza | 0 | 2014-01-16
Cornel V. dela Cruz | 0 | 2014-01-16
Gerardo R. Santos | 0 | 2014-01-09
Aurora L. Bacay | 0 | 2014-01-09
Edwin B. Sison | 0 | 2014-01-08
Merlyn Y. Adan - | 49600 | 2016-03-30 | cash advance of Reg.fees, transportation expenses & per diems in attendance to the Training on Learning & Dev't Planning at Quezon City on April 7-8, 2016 |  | 49600
Irmina B. Francisco | 404200 | 2016-03-16 | Cash advance to defray expenses for Gov. Amado T. Espino, Jr. Academic Excellence Award & Leadership Excellence Award for Academic Year 2015-2016 |  | 404200
Emilio P. Samson, Jr. | 181300 | 2016-03-15 | (PR#2899) - payment of cash advance re: to join & participate of Persons w/ Disabilities delegates in the 5th stage of PHILSPADA National PARA Games on Mar.28-April 2, 2016 at Marikina Sports, Marikina City |  | 181300
Edgardo D. Ancheta | 14000 | 2016-03-09 | cash advance for payment of per diems, transportation expenses & reg. fee in connection with his attendance to the 30th Annual Technical Consultative Workshop Conference at Bohol Plaza Resort & Restaurant, Dayo Hill, Mayacabac, Dauis, Bohol on Apr.5-8, 2016 |  | 14000
Arnold O. Nieto - | 14000 | 2016-03-09 | cash advance for payment of per diems, travelling expenses & reg. fee in connection with his attendance to the 30th Annual Technical Consultative Workshop Conference at Bohol Plaza Resort & Restaurant, Dayo Hill, Mayacabac, Dauis, Bohol on Apr.5-8, 2016 |  | 14000
Antonieta C. Delos Santos | 100000 | 2016-03-04 | Cash advance to be used for the preparation of 2016 Phil. National Games on Mar.7-11, 2016 at NRSCC, Lingayen, Pangasinan |  | 100000
Mirasol J. Mina | 8851.68 | 2016-03-04 | Cash advance per diems & other incidental expenses to attend the Prov'l Health Officers Association of the Phil.(PHOAP) National Convention to be held in Iloilo City on Mar.15-17, 2016 |  | 8851.68
Dra. Anna Ma. Teresa S. De Guzman | 8851.68 | 2016-03-04 | cash advance per diems & other incidental expenses to attend the Prov'l Health Officers Association of the Phil.(PHOAP) National Convention to be held in Iloilo City on Mar.15-17, 2016 |  | 8851.68
Joenard E. Manuel - | 25688 | 2016-02-24 | payment of cash advance for Trav.exps., per diems, reg. fee, accomm. & other exps. to attend in the training on ISO 9001:2008 Quality Management Awareness on Mar.2, 2016, Internal Quality Audit on Mar.9-10, 2016 & Training on Effective IQA Report Writing on Mar.11, 2016 to be held at PTTC, Pasay City |  | 25688
Rowena Brenda O. Guiang - | 35748 | 2016-02-24 | payment of cash advance for Trav.exps., per diems, reg. fee & other exps. to attend in the training on ISO 9001:2008 Quality Management Awareness on Mar.2, 2016 & Training on Effective IQA Report Writing on Mar.11, 2016 to be held at PTTC, Pasay City |  | 35748
Joan Jenny M. Garacho - | 65400 | 2016-02-18 | cash advance of reg.fees, per diems, transportation & misc. exps.in attendance to the training on "Emotional Disturbance Among Children in Residential Centers" on Mar.3-4 at the Exec. Lounge of WSI Corporate Center, Makati City |  | 65400
Alex F. Ferrer | 70000 | 2016-02-17 | Cash advance to defray expenses for the tokens/raffle prizes, stage decoration & etc. during the conduct of OFW Congress on Feb.25, 2016 |  | 70000
Jocelyn J. Mariñas - | 19130 | 2016-02-12 | cash advance to defray expenses to attend the Annual Convention of PHILBO on March 1-4, 2016 at Lahug, Cebu |  | 19130
Purificacion N. Bermudez - | 19130 | 2016-02-12 | cash advance to defray expenses to attend the Annual Convention of PHILBO on March 1-4, 2016 at Lahug, Cebu |  | 19130
Ramon M. Morden | 300000 | 2016-02-05 | Financial Assistance to be given to diff. constituents of Pangasinan |  | 300000
Emilio P. Samson, Jr. RSW | 50000 | 2016-02-04 | Payment of cash advance re: financial assistance to indigents |  | 50000
Natividad F. Sabangan - | 16060 | 2016-02-04 | payment of her Cash Advance for reg.fee, traveling exps.& per diems in attending the Philippine League of Local Budget Officers (PHILLBO), Inc. in Mar.1-4, 2016 at Grand Convention Center of Cebu, Cebu City |  | 16060
Gerardo R. Santos - | 16060 | 2016-02-04 | payment of his Cash Advance for reg.fee, traveling exps.& per diems in attending the Philippine League of Local Budget Officers (PHILLBO), Inc. in Mar.1-4, 2016 at Grand Convention Center of Cebu, Cebu City |  | 16060
Dondelina S. Catabay - | 16060 | 2016-02-04 | payment of her Cash Advance for reg.fee, traveling exps.& per diems in attending the Philippine League of Local Budget Officers (PHILLBO), Inc. in Mar.1-4, 2016 at Grand Convention Center of Cebu, Cebu City |  | 16060
Cristina J. Bumiltac | 465268.9 | 2016-01-27 | Cash advance in payment of various foodtuff & other operational expenses for use at Capitol Resort Hotel |  | 465268.9
Antonieta C. Delos Santos | 250000 | 2016-01-20 | Cash advance to be used for the Immediate Repair of various Prov'l Bldgs., Service Vehicles & Equipment |  | 250000
Irmina B. Francisco | 300000 | 01/15/2016 | Cash advance for financial assistance for cultural presentation to be given to diff. constituents of the Province of Pangasinan |  | 300000
Ma. Luisa A. Elduayan | 103000 | 01/5/2016 | Cash advance to defray expenses for the incoming 71st Anniversary of the Lingayen Gulf Landings & 9th Veteran's Day on Jan.9, 2016 |  | 103000
Salvador Vedaña | 10000 | 2003-10-08 | Traveling Expenses | [5 empty] | 10000
Judge Dionisio C. Sison | 7000 | 2001-07-16 | [6 empty] | 7000
Eugenio G. Ramos | 2500 | 1999-04-14 | [6 empty] | 2500
BM Eduardo Perez, Sr. | 5000 | 1999-02-03 | Traveling Expenses | [5 empty] | 5000
BM Rogelio Law | 5000 | 1997-09-22 | Traveling Expenses | [5 empty] | 5000
Atty. Feliciano M. Bautista | 1200 | 1997-07-22 | Traveling Expenses | [5 empty] | 1200
Roderick Mina | 3600 | 1997-06-22 | Traveling Expenses | [5 empty] | 3600
Rodolfo M. Cortez | 30000 | 1997-04-10 | [6 empty] | 30000
BM Leonardo Caranto | 20000 | 1997-02-27 | Traveling Expenses | [5 empty] | 20000
Rodolfo M. Cortez | 20000 | 1996-06-20 | [6 empty] | 20000
Maximu Dulay | 5000 | 1989-06-16 | [6 empty] | 5000
Federico Victorio | 1500 | 1985-04-30 | Traveling Expenses | [5 empty] | 1500
Rodolfo Rivera | 1300 | 1983-06-04 | Traveling Expenses | [5 empty] | 1300
Rodolfo Itchon | 1500 | 1982-05-07 | Traveling Expenses | [5 empty] | 1500
Rodolfo Itchon | 1000 | 1981-03-19 | Traveling Expenses | [5 empty] | 1000
Rodolfo Rodrigo | 500 | 1978-11-23 | Traveling Expenses | [5 empty] | 500
Narciso Ramos | 1250 | 1978-08-28 | Traveling Expenses | [5 empty] | 1250
Felipe Santillan | 1250 | 1978-02-28 | Traveling Expenses | [5 empty] | 1250
Total | 2649948.26 |  |  |  | 2532348.26 |  |  |  | 117600
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA |  |  |  |  | AMADO T. ESPINO, JR
Provincial Accountant |  |  |  |  | Governor