## 20%ira
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1ST QUARTER, CY 2017
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Labor, materials, equipment and other incidentals for the construction of Multi-purpoose Bldg. (covered court) | Sagud Bahley, San Fabian | 2397033 | 2017-02-27 | on going | 35% | 838961.55 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the construction of Bleacher | Municipal Plaza at Calasiao | 4092437 | 2017-02-20 | on going | 70% | 2864705.9 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the proposed repair/rehabilitation of roofing of Multi-purpose Hall @ New Cemetery | Brgy. Ketegan, Bautista | 706555 | 2017-04-03 | on going | 60% | 423933 |  | OBLIGATED
Labor, materials and other incidentals for the floor slab Elevation and Extension of 5-span of covered court | Brgy. Dumpay, Basista | 2770458 | Not yet started |  |  | 0 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the construction of covered court | Brgy. Sinabaan, Bautista | 2466115 | 2017-02-27 | on going | 45% | 1109751.75 |  | OBLIGATED
Labor, materials, equipment and other incidentals necessary for the Rehabilitation of Swimming Pool at NRSCC | Lingayen | 3500000 | 2017-03-22 | on going | 8% | 280000 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the rehabilitation of Bleachers, shower rooms, comfort rooms and fence at swimming pool, NRSCC, Lingayen | Lingayen | 1881736 | 2017-03-23 | on going | 9% | 169356.24 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the rehabilitation and repair of Drainage and elevation of concrete pavement at Zone 4, Pangapisan Sur, Lingayen | Lingayen | 2347446 |  |  |  | 0 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the construction/improvement of MPC Bldg., | Asingan | 1244427 | 2017-03-08 | on going | 70% | 871098.9 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the construction of Brgy. Health Center at Brgy. Landas, Mangaldan |  | 892224 |  |  |  | 0 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the repair/rehabilitation of Multi-Purpose Hall at Brgy. Awai, San Jacinto |  | 440029 |  |  |  | 0 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the construction of drainage canal w/ cover at Brgy. Polong Norte, Malasiqui |  | 380146 |  |  |  | 0 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the construction of CHB Drainage Canal (Continuation) at Brgy. Cabalitian, Asingan |  | 470093 |  |  |  | 0 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the improvement/repair of Health Center at Brgy. Coliling, Rosales |  | 736015 |  |  |  | 0 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the construction of Solar Dryer at Brgy. Salavante, Mangatarem |  | 787264 |  |  |  | 0 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the construction of drainage canal w/ concrete cover at Abalos St., Mangaldan |  | 768069 |  |  |  | 0 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the construction of covered court (steel col) phase II, Brgy. Paitan, Sta. Maria |  | 1937240 |  |  |  | 0 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the construction of Multi-purpose Hall 2-Storey Bldg. at Brgy. Labney, San Jacinto |  | 1551361 |  |  |  | 0 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the construction of Drainage Canal at Amansabina, Mangaldan |  | 1998054 |  |  |  | 0 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the completion of 2-storey Brgy. Hall Bldg., at Brgy. Lipay, Villasis |  | 1330456 |  |  |  | 0 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the the Improvement of 2-storey Multi-Purpose Bldg., (Brgy. Hall) at Brgy. Magallanes (Phase 1), | Tayug | 2098660 | 2017-04-24 | on going | 1% | 20986.6 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the construction of covered court at Brgy. Banaoang, Mangaldan |  | 1853962 | [5 empty] | OBLIGATED
Labor, materials, equipment and other incidentals for the improvement/extension of Municipal Hall Bldg., Bugallon |  | 5807123 | [5 empty] | OBLIGATED
Labor, materials, equipment and other incidentals for the construction of 2-storey Training Center at Poblacion, Alcala |  | 8000000 | [5 empty] | OBLIGATED
Labor, materials, equipment and other incidentals for the construction/rehab of various facilities for Drug Rehabilitation Center | Brgy. San Vicente, Burgos, Pangasinan | 2288767 | 2017-02-15 | on going | 57.58% | 1317872.0386 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the repair/improvemet of Labrador Municipal Hosp., | Poblacion, Labrador | 2057604 |  |  | 40% |  |  | OBLIGATED
120 pcs. Knapsack sprayer |  | 498000 | [5 empty] | OBLIGATED
Labor, materials, equipment and other incidentals for the replacement of roofing & rewiring of Main Bldg., Phase 1 at | Mapandan | 1593591.03 | 2017-03-20 | on going | 12% | 191230.9236 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the construction/provision of a) consruction/improvement of drainage system b) Waiting Area w/CR (Male/female) at Bayambang Dist. Hospital, Bayambang |  | 1032137 |  |  |  | 1309553.66 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the improvement of covered court and construction of perimeter fence with gate of Brgy. Hall Cmpd. At Malabobo, Mangatarem |  | 995938 |  |  |  | 1309553.66 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the construction of Day Care Center with CR and Lavatory at Brgy. Cabarabuan, Mangatarem |  | 938100 |  |  |  | 1309553.66 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the proposed construction of Additional decaying Pit Chamber at Urdaneta Dist. Hospital, Urdaneta |  | 214282 |  |  |  | 1309553.66 |  | OBLIGATED
Various materials for the construction of 16 units portalets and 5 units bambboo arc at OPAG, Sta. Barbara |  | 131415 |  |  |  | 1309553.66 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the upgrading of MTS Panel, MCB Panel, Feederline at PESO, PRAC & Prov'l Legal Office Bldgs., Lingayen |  | 974485 |  |  |  | 1309553.66 |  | OBLIGATED
Labor, materials, equipment and other incidentals necessary for the proposed 6 units bleacher at PNP Lingayen |  | 1535973 |  |  |  | 1309553.66 |  | OBLIGATED
Various materials for the installation of Bamboo Poles for the Pistay Dayat 2017 Banner at PTDC & Capitol Beachfront and Construction of Washing area at Veterans Park Area, Lingayen |  | 128343 |  |  |  | 1309553.66 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the repair of 1-unit day care center at Brgy. Sapinit, San Carlos City |  | 96569 |  |  |  | 1309553.66 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the concreting of solar dryer at Brgy. Gomez, Malasiqui |  | 618210 |  |  |  | 1309553.66 |  | OBLIGATED
100 units 7 HP air cooled diesel engine couple w/ 3" diameter pump with accessories |  | 2400000 |  |  |  | 1309553.66 |  | OBLIGATED
Labor, materials, equipment and other incidentals-construction of 1 unit water system (excavation, drilling & installation of motorpump) at Buer-Bayaoas E/S, Aguilar |  | 234960 |  |  |  | 1309553.66 |  | OBLIGATED
Labor, materials, equipment and other incidentals-construction of 2 units artesian well (deep well) at Sitio Silag & Allabon Proper, Brgy. Allabon, Agno |  | 457700 |  |  |  | 1309553.66 |  | OBLIGATED
140 pcs jetmatic pump and 280 pcs. GI Pipes 1-1/4" O 20' sch. 40. |  | 995400 |  |  |  | 1309553.66 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the construction of 2 units Artesian Well @ Brgy. Castaño, Pozorrubio |  | 263200 |  |  |  | 1309553.66 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the construction of 2 units Artesian Well @ Brgy. Villegas, Pozorrubio |  | 258600 |  |  |  | 1309553.66 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the construction of 2 units Artesian Well @ Brgy. Sablig, Anda |  | 263200 |  |  |  | 1309553.66 |  | OBLIGATED
Construction materials for the construction of 2 units Artesian Well at Brgy. Palisoc, Bautista, Pangasinan |  | 57186 |  |  |  | 1309553.66 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the construction of 2 units Artesian Well | Brgy. Sta. Maria East, San Nicolas | 320620 | 2017-04-05 | on going | 85% | 272527 |  | OBLIGATED
Various materials for the construction of 2 units deep well at Brgy. Ambayat 2nd, Bayambang |  | 64666 |  |  |  | 1309553.66 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the construction of 2 units Artesian Well at Brgy. Fianza, San Nicolas |  | 263200 |  |  |  | 1309553.66 |  | OBLIGATED
Various materials for the construction of 2 units deep well at Brgy. Dusoc, Bayambang |  | 60986 |  |  |  | 1309553.66 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the construction of 1 unit deep well | Brgy. Canaoalan, Binmaley | 543200 | 2017-03-18 | on going | 96% | 521472 |  | OBLIGATED
2 units Sub:2 3/8" Mayhew Jr. Box to 3 1/2 API Reg. Box (Weight: 16:3 lbs., Dimension: 10" Lx 4 1/2" W) |  | 1513000
Various materials for the construction of 2 units deep well (1 unit with jetmatic pumphead and 1 unit with motorpump) at Castusu Integrated School Casantiagoan, Laoac |  | 89039
Labor, materials, equipment and other incidentals for the construction of two (2) units Artesian Well (w/ excavation) at San Eugenio, Natividad |  | 183100
2 and 10 rolls 1" dia. PE Pipe SDR 11 and 3/4" dia. PE Pipe SDR 11, respectively, for the provision of PE Pipe for connection of potable drinking water at Brgy. Babuyan, Infanta |  | 79500
Sub-total |  | 69743235.03 |  |  |  | 36382522.7622
Economic Development
Labor, materials, and other incidentals for the concreting of road with drainage canal at Luneta St., Brgy. Libsong East, Lingayen |  | 1994929
Labor, materials and other incidentals for the improvement (concreting) of road at Mendoza St., Brgy. Libsong West, Lingayen |  | 1930779
Labor, materials, equipment and other incidentals for the concreting of Malasiqui-Catablan Road, Malasiqui, as per Extra Work Order #1 |  | 644644.66
Labor, materials, equipment and other incidentals for the rehabilitation/ improvement/ upgrading of Bugos-Iliw-Iliw Road, Burgos, as per Extra Work Order #2 |  | 596210.15
1652 MT Asphalt Pre-mix, 66 drums E. Asphalt for the improvement (patching/blocktopping) of various provincial Roads |  | 10036400
Labor, materials, equipment and other incidentals for the construction of stone masonry at Brgy. Guibel, San Jacinto |  | 676726
Labor, materials, and other incidentals for the concreting of road with RCCP at Brgy. Rizal Rosales |  | 1561402
Labor, materials, equipment and other incidentals for the concreting of Brgy. Salvacion Road, Rosales |  | 2749318
Labor, materials, equipment and other incidentals for the proposed concreting of Sta. Isabel Road, Brgy. Palaris, San Carlos City |  | 587832
Labor, materials, equipment and other incidentals for the concreting of Farm to Market Road Sitio Guilig, Guevara Road, Brgy. Guesang at Mangaldan |  | 1930272
Labor, materials, equipment and other incidentals for the concreting of Farm to Market Road at Calejon Road infront of Nibaliw E/S, Mangaldan |  | 1030392
Labor, materials, equipment and other incidentals for the concreting of Farm to Market Road at Brgy. Buaya, Mangatarem |  | 2205100
Labor, materials, equipment and other incidentals for the proposed concreting of Porok Ilang-ilang Road, Dahlia Road, Rosal Road at Brgy. Buer, Aguilar |  | 2151904
Labor, materials, equipment and other incidentals for the proposed concreting of New Street East Poblacion, Lingayen |  | 2947317
Labor, materials, equipment and other incidentals for the proposed concreting of Sitio Tanggal at Brgy. Lapa, Malasiqui |  | 1598914
18 MT Asphalt Pre-mix and 6 drums Emulsified Asphalt used for asphalting/blocktopping of Lambayan Brgy. Road, Mapandan |  | 1098400
449 MT Asphalt Pre-mix and 15 drums for the asphalting/blocktopping | Domalandan-Balangobong Road, Lingayen | 2685500 | 2017-04-25 | 2017-04-28 | 100% | 2685500 |  | OBLIGATED
460 MT Asphalt Pre-mix and 20 drums E. Asphalt for the asphalting of Brgy. Road, Brgy. Centro Toma, Bani |  | 2818000 | [5 empty] | OBLIGATED
5 drum E. Asphalt & 110 MT Asphalt Pre-mix for asphalting of Brgy. Sto. Tomas Road, San Jacinto |  | 677000 | [5 empty] | OBLIGATED
644 MT Asphalt Pre-mix and 28 drums emulsified Asphalt for the asphalting of Baruan Road, Brgy. Baruan, Agno |  | 3945200 | [5 empty] | OBLIGATED
Labor, materials, equipment and other incidentals for the proposed concreting of road | Brgy. Bocboc West, Aguilar | 2975206 | Not stated |  | 50% | 1487603 |  | OBLIGATED
Labor, material, equipment and other incidentals for concreting | Brgy. Panakol Road, Aguilar | 1923273 | Not stated |  | 90% | 1730945.7 |  | OBLIGATED
Labor, material, equipment and other incidentals for the concreting of Purok 6 at Brgy. Sapinit, San Carlos City |  | 1452787 | [5 empty] | OBLIGATED
Labor, materials, equipment and other incidentals necessary for the concreting of farm to market road, Brgy. Golden, Mapandan |  | 1381703 | [5 empty] | OBLIGATED
Labor, materials, equipment and other incidentals for the concreting of Sitio Baleno at Brgy. Warey, Malasiqui |  | 1407086 | [5 empty] | OBLIGATED
Labor, materials, equipment and other incidentals for the concreting of Maligaya-Sitio Banaolan Rd., Brgy. Palaming, San Carlos City |  | 2222210 | [5 empty] | OBLIGATED
86 MT Asphalt Pre-mix and 4 drums Emulsified Asphalt for asphalting/ blocktopping | Brgy. Road at Brgy. San Pablo, Binanalonan | 530600 | 2017-03-30 | 2017-03-31 | 100% | 530600 |  | OBLIGATED
Labor, material, equipment and other incidentals for concreting | Sitio Pungis at Brgy. Warey, Malasiqui | 1475536 | 2017-04-04 | on going | 80% | 1180428.8 |  | OBLIGATED
Labor, materials, equipment and other incidentals necessary for the concreting of farm to market road, Brgy. Dorongan Sawat, Mangatarem |  | 2545900 | [5 empty] | OBLIGATED
Labor, materials, equipment and other incidentals for the improvement/rehabilitation of Sapang Bridge, Mangatarem |  | 4110571 | [5 empty] | OBLIGATED
159 MT Asphalt Pre-mix and 5 drums for use of Blocktopping | Brgy. Antonio Village Road, Rosales | 946500 | 2017-04-06 | 2017-04-08 | 100% | 946500 |  | OBLIGATED
288 MT Asphalt Pre-mix and 9 drums for use of blocktopping | Zone 4 Road at Rosales | 1713600 | 2017-04-01 | 2017-04-03 | 100% | 1713600 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the rehabilitation of Taculit Bridge I (6 L.M.) | San Fabian | 2030275 | Not stated |  | 6% | 121816.5 |  | OBLIGATED
Labor, materials, equipment and other incidentals for the construction of hanging bridge | Brgy. Garrita, Bani | 2171408 | Not stated |  | 5% | 108570.4 |  | OBLIGATED
184 MT Asphat Pre-mix and 8 drums emulsified asphalt for the asphalting of Brgy. Cacandungan Road, Bautista |  | 1127200
Labor, materials, equipment and other incidentals for the concreting of Brgy. Pita Road, Infanta |  | 1500000
Labor materials, equipment and other incidentals for the construction of 1 unit 2 barrel RCBC (6.60) L.M.) at Manaoag |  | 1804553
Labor, materials, equipment and other incidentals necessary for the Rehabilitation of Taculit Bridge II (6 L.M.) at San Fabian |  | 2030275
1444 MT Pre-mix for blocktopping of various roads within the province |  | 7942000
Amortization of Principal and Interest on Loan to the LBP |  | 59426558.79
Loans Granted to MPC's/ Livelihood Assoc'n |  | 3730000
414 MT of Asphalt Pre-mix for blocktopping of Perez St., Brgy. Poblacion, San Manuel |  | 2277000
Labor, materials, equipment and other incidentals for the construction of 1 unit 3 barrel RCBC with Slope Protection & Concreting of Road along Mabini Breeding Station (10.20) L.M.) at Mabini |  | 3177866
Labor, materials, equipment and other incidentals for the installation of 57 units of STWIP of various barangays and Municipality of Pangasinan, District I-IV |  | 4170996.09
Engine pumpset and other incidentals for the installation of 20 units STWIP (Open Well) |  | 704550
Sub-total |  | 114572941.79 |  |  |  | 10505564.4
Environmental Development
Grand Total |  | 184316176.82 |  |  |  | 46888087.1622
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
CATHERINE DC. CAMBA, CPA |  |  |  |  | HON. AMADO I. ESPINO, III
Officer in Charge-Provincial Accounting Office |  |  |  |  | Governor

## LDRRM
FDP Form 8 - Local Disaster Risk Reduction and Management Fund Utilization
(COA Form)
LOCAL DISASTER RISK REDUCTION AND MANAGEMENT FUND UTILIZATION
For The Quarter January to March 2017
Province of Pangasinan
LDRRMF
Particulars | Quick Response | Mitigation Fund | NDRRMF | From Other LGUs | From Other Sources | Total
| Fund (QRF) | 70%
30%
A. Sources of Funds:
Current Appropriation | 52233739 | 121878725.5
Continuing Appropriation |  | 9512025
Previous Year's Appropriation transferred to the Special Trust Fund |  | 97152215.91
Transfers/Grants | [5 empty] | 0
Others ( Please specify) | [5 empty] | 0
Total Funds Available | 52233739 | 228542966.41 | 0 | 0 | 0 | 280776705.41
B. Utilization
Medicines
Medical Supplies
Food Supplies |  | 52500
Office Supplies
Repair of Evacuation Center
Disaster Response & Rescu Equipment
Institutional/Capacity Development ( Ex. Trainings, environmental assessment & other related activities)
Construction of Evacuation Center
Capital Outlay - Equipment |  | 2962290
Transfer to other LGUs
Other Maintenance and Operating Expenses |  | 1789762.75
Traveling Expense
Training Expense |  | 10980
IT Equipment & Software
Motor Vehicles
Other Machineries and Equipment
Watercrafts
Other Property, Plant and Equipment
Roads, Highways and Bridges |  | 16081344.36
Communication Equipment
Gasoline, Oil, Lubricants |  | 309898.52
Furniture & Fixtures
Donations
Repair/Rehabilitation of Public Infrastructures, Roads, Highways and Bridges, etc.
Repair & Maintenance- Building & Other Structures |  | 53027
Honorarium |  | 42000
Furnitures & Fixtures
Repair & Maintenance-Motor Vehicles
Total Utilization | 0 | 21301802.63 | 0 | 0 | 0 | 21301802.63
Unutilized Balance | 52233739 | 207241163.78 | 0 | 0 | 0 | 259474902.78
I hereby certify that I have reviewed the contents and hereby attest to the veracity and correctness of the data or
information containedin this document.
CATHERINE DC. CAMBA, CPA
Officer In Charge-PACO

## SEF
FDP Form 11 - SEF Utilization
(SEF Budget Accountability Form No. 1)
REPORT OF SEF UTILIZATION
For the Quarter Ending March 31, 2017
Province/City Municipality |  | Pangasinan
Receipt from SEF |  |  |  | 67698022.55
Less: | DISBURSEMENTS (broken down by expense class and by object of expenditure)
Personal Services
-0-
Maintenance and Other Operating Expenses
13547781.51
Capital Outlay
-0-
Financial Expenses
-0-
Sub-total |  |  |  | 13547781.51
Balance |  |  |  | 54150241.04
We hereby certify that we have reviewed the
contents and hereby attest to the veracity and
correctness of the data or information
contained in this document.
CATHERINE DC. CAMBA, CPA
Officer in Charge-Provincial Accounting Office
HON. AMADO I. ESPINO, III
Governor
Note on I11: Pangasinan Accounting:

## CASHFLOWS
FDP Form 9 - Statement of Cash Flow
(COA Form)
PROVINCE OF PANGASINAN
Statement of Condensed Cash Flows
GENERAL FUND
For the First Quarter Ending March 31,2017
Cash Flows from Operating Activities:
Cash Inflows:
|  | Collection from Taxpayers |  | 58800964.11
|  | Share from Internal Revenue Allotment |  | 740407314
|  | Receipts from business/service income |  | 92907027.95
|  | Interest Income |  | 1098364.8
|  | Other Receipts |  | 38840140.51
|  | Total Cash Inflow |  | 932053811.37
Cash Outflows:
|  | Payment of expenses |  | 318593081.63
|  | Payment to suppliers and creditors |  | 192355680.31
|  | Payment to employees |  | 191241881.16
|  | Interest Expenses |  | 12152966.3
|  | Other Expenses |  | 65837927.99
|  | Total Cash Outflow |  | 780181537.39
| Net Cas Flows from Operating Activities |  |  | 151872273.98
Cash Flows from Investing Activities:
Cash Inflows:
|  | Proceeds from Sale of Investment Property |  | 0
|  | Proceeds from Sale/Disposal of Property, Plant and Equipment |  | 0
|  | Collection of Principal on Loans to other Entities |  | 1635000
|  | Total Cash Inflow |  | 1635000
Cash Outflows:
|  | Purchase / Construction of Investment Property |  | 0
|  | Purchase / Construction of Property, Plant and Equipment |  | 120838702.37
Purchase of Bearer Biological Assets
|  | Grant of Loans |  | 1760000
|  | Total Cash Outflow |  | 122598702.37
| Net Cash Flows from Investing Activities |  |  | -120963702.37
Cash Flows from Financing Activities:
Cash Inflows:
|  | Proceeds from Loans |  | 35526480.75
|  | Total Cash Inflow |  | 35526480.75
Cash Outflows:
|  | Payment of Long-Term Liabilities |  | 0
|  | Payment of Loan Amortization |  | 48368592.49
|  | Total Cash Outflow |  | 48368592.49
| Net Cash Flows from Financing Activities |  |  | -12842111.74
Total Cash Provided by Operating,Investing and
|  | Financing Activities |  | 18066459.87
Add:Cash at Beginning of the Quarter |  |  |  | 1236728223.55
Cash at the End of the Quarter |  |  |  | 1254794683.42
Certified Correct:
CATHERINE DC. CAMBA, CPA
Officer In Charge-PACO

## TRUST FUND
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE JANUARY - MARCH QUARTER, CY 2017
Province : PANGASINAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
payment of 90% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Asingan-San Miguel-Agno Gorge Road, Asingan, Pangasinan | Asingan, Pangasinan | 3748730.47 |  |  | 90% | 3748730.47 |  | fund from the Department Public Works and Highways
payment of 100% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Malasiqui-Catablan Road, Malasiqui, Pangasinan | Malasiqui, Pangasinan | 4496446.7 |  |  | 100% | 4496446.7 |  | fund from the Department Public Works and Highways
payment of 100% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Talac Boundary-Bayambang Diversion Road, Bayambang, Pangasinan | Bayambang, Pangasinan | 4496955.34 |  |  | 100% | 4496955.34 |  | fund from the Department Public Works and Highways
payment of 100% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Mangatarem-Urbiztondo Road,Mangatrem, Pangasinan | Mangatarem, Pangasinan | 1795050.24 |  |  | 100% | 1795050.24 |  | fund from the Department Public Works and Highways
payment of IT equipment and accessories for the implementation of Bottom-Up Budgeting in Sta. Barbara, Pangasinan Local Regional Economic Development Streamlining Business Permits and Licensing System | Sta. Barbara, Pangasinan | 70230 |  |  |  | 70230 |  | fund from the Department of Trade and Industry
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
CATHERINE DC. CAMBA | [5 empty] | HON. AMADO I. ESPINO, III
Officer-In-Charge, Provincial Accounting Office | [5 empty] | Governor

## UNLIQUIDATED
FDP Form 12- Unliquidated Cash Advances
UNLIQUIDATED CASH ADVANCES
As of March 31, 2017
Province, City or Municipality: | PANGASINAN
Name of Debtor (in alphabetical order) | Amount Balance | Date Granted | Purpose | Amount Due
|  |  |  | Current |  |  | Past Due
|  |  |  | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
Rommel Cardinoza | 0 | 2014-01-16
Cornel V. dela Cruz | 0 | 2014-01-16
Gerardo R. Santos | 0 | 2014-01-09
Aurora L. Bacay | 0 | 2014-01-09
Edwin B. Sison | 0 | 2014-01-08
Advances for Officers and Employees
Pia Merrielle M. Balagot | #REF! | 2017-03-01 | cash advance for registration fee, travelling expenses and other expenses in connection with her official trip to SM | 22355
Grace B. Saringan | #REF! | 2017-03-01 | payment of cash advance for registration fee, travelling expenses and other expenses inc onnection with her official trip to SM Lanang, Davao City to attend the Phil. League of Local Budget Officer April 4-7, 2017 | 22355
Jeanne R. Evangelista | #REF! | 2017-03-15 | payment of her cash advance for her attendance to the 22nd Regional Contuing Professional Education for HMM Practitioner at Kultura Splash Wave, La Union April 4-6, 2017 | 8100
Col. Rhodyn Luchinvar O. Oro | #REF! | 2017-03-15 | cash advance to defray expenses in their official travel to San Fernando, Camarines Sur on March 16-18, 2017 to handover the Check representing financial assistance | 60000
Emilio P. Samson Jr. | #REF! | 2017-03-15 | cash advance to defray expenses for their office travel to Surigao Cit march 15-18, 2017 | 77850
Fe Consuelo V. Andrade | #REF! | 2017-03-15 | payment of cash advance for her registration fee, traveling expense and per diems, in connection with her attendance to attend the 22nd Regional Continuing Professional Education for HRMDO April 4-6, 2017 | 7500
Aurora L. Bacay | #REF! | 2017-03-15 | payment of her cash advance for her registration fee, travelling expense and per diems, in connection with her attendance to attend the 22nd Regional Continuing Professional Education HRM practitioners April 4-6, 2017 | 7500
Nathaniel Joel M. Daroy | #REF! | 2017-03-21 | cash advance the amount to defray in attending the "Plotting for Museum Practitioners in the Philippines on March 30 - April 1, 2017 to be held at the University of Santo Tomas, manila | 18300
Vivian U. Oamil | #REF! | 2017-03-23 | cash advance expenses to be incurred in attending the 16th Regional Mining Summit March 29-31, 2017 at the Puerto de San Juan Resort Hotel, Ili Sur, San Juan La Union | 7560
Juliet F. Robina | #REF! | 2017-03-23 | cash advance expenses to be incurred in attending the 16th Regional Mining Summit March 29-31, 2017 at the Puerto de San Juan Resort Hotel, Ili Sur, San Juan La Union | 7560
Mixon D. Flores | #REF! | 2017-03-23 | cash advance expenses to be incurred in attending the 16th Regional Mining Summit March 29-31, 2017 at the Puerto de San Juan Resort Hotel, Ili Sur, San Juan La Union | 7560
Evelyn C. Dismaya | #REF! | 2017-03-23 | cash advance re:Community Based Drug Demand Reduction, Treatment, Rehabilitation and After Case Services | 94200
Elmar Z. De Guzman | #REF! | 2017-03-27 | cash advance expenses to be incurred in attending the 16th Regional mining summit March 29-31, 2017 at the Puerto De San Juan resort Hotel, Ili Sur, San Juan La Union | 7560
Ms. Hendralyn E. Macaraeg | #REF! | 2017-03-28 | cash advance pymt of her Training fee, per diems,. And her Transportation expenses | 8310
Helen Gay Sadorra | #REF! | 2017-03-31 | cash advance for training expenses on the conduct of 2017 Annual Convention on of Association of medical social worker of the Philippines Incorporated (AMSWPI) April 19-21, 2017 | 8000
Hon. Jeanne Jinky C. Zaplan | #REF! | 2017-02-08 | cash advance of registration fee/travelling expenses to attend the 27th National Convention of the Prov'l Board member League of the Philippines on Feb. 27 to March 1, 2017 |  | 30000
Hon. Clemente B. Arboleda, Jr. | #REF! | 2017-02-08 | cash advance of registration fee/Travelling expenses to attend the 27th National Convention of the Prov'l League of the Philippines on Feb 27 to March 1, 2017 |  | 30000
Hon. Jeremy Agerico B. Rosario | #REF! | 2017-02-08 | cash advance of registration fee/travelling expenses to attend the 27th National Convention of the Prov'l Board Members League of the Philippines on Feb. 27 to March 1, 2017 |  | 30000
Hon. Liberato Z. Villegas | #REF! | 2017-02-08 | cash advance of registration fee/travelling expenses to attend the 27th National Convention of the Prov'l Board Members League of the Philippines on Feb. 27 to March 1, 2017 |  | 30000
Hon. Antonio F. Sison | #REF! | 2017-02-09 | cash advance of Registration fee/travelling expenses to attend the 27th National Convention of the Prov'l Board Members League of the Philippines Feb. 27 to March 1, 2017 |  | 30000
Hon. Generoso D. Tulagan, Jr. | #REF! | 2017-02-10 | cash advance of registration fee/travelling expenses to attend the 27th National Convention of the prov'l Board members league of the Philippines Feb. 27 to March 1, 2017 |  | 30000
Hon. Napoleon C. Fontelera, Jr. | #REF! | 2017-02-13 | cash advance of registration fee/travelling expenses to attend thye 27th national Convention of the Prov'l league Board members of the Philippines on Feb. 27 to March 1, 2017 |  | 30000
Baby S. Torio | #REF! | 2017-02-20 | payment of cash advance to defray expenses, per diems,, registration fee and others during the official travel to Davao City on March 14-17, 2017 to attend National Conference of Librarians with a theme "The Emerging of Libraries: connect, collaborate and build strong communities |  | 19754.56
Marife P. Acerit | #REF! | 2017-02-22 | cash advance to defray expenses of the Dangoan pangasinan dance Troupe will perform and to represent the province for the 1st Indak Pilipinas: 2017 Philippine Traditional Dance Festival March 7-9, 2017 at the Tanghalang Aurelio Tolentino Little Theater of the Cultural Center |  | 116400
Joan Jenny M. Garacho | #REF! | 2017-02-24 | payment of cash advance re:Seminar on Case management for Residential Facility Workers & Administrators March 3-4, 2017 |  | 63000
Hilaria J. Claveria | #REF! | 2017-02-27 | payment of cash advance for registration fee, travelling expenses and other expenses in connection with her official trip to SM lanang, Davao City to attend the Philippines League of Local Budget Officers April 4-7, 2017 |  | 26355
Salvador Vedaña | 10000 | 2003-10-08 | Traveling Expenses | [5 empty] | 10000
Judge Dionisio C. Sison | 7000 | 2001-07-16 | [6 empty] | 7000
Eugenio G. Ramos | 2500 | 1999-04-14 | [6 empty] | 2500
BM Eduardo Perez, Sr. | 5000 | 1999-02-03 | Traveling Expenses | [5 empty] | 5000
BM Rogelio Law | 5000 | 1997-09-22 | Traveling Expenses | [5 empty] | 5000
Atty. Feliciano M. Bautista | 1200 | 1997-07-22 | Traveling Expenses | [5 empty] | 1200
Roderick Mina | 3600 | 1997-06-22 | Traveling Expenses | [5 empty] | 3600
BM Leonardo Caranto | 20000 | 1997-02-27 | Traveling Expenses | [5 empty] | 20000
Maximu Dulay | 5000 | 1989-06-16 | [6 empty] | 5000
Federico Victorio | 1500 | 1985-04-30 | Traveling Expenses | [5 empty] | 1500
Rodolfo Rivera | 1300 | 1983-06-04 | Traveling Expenses | [5 empty] | 1300
Rodolfo Itchon | 1500 | 1982-05-07 | Traveling Expenses | [5 empty] | 1500
Rodolfo Itchon | 1000 | 1981-03-19 | Traveling Expenses | [5 empty] | 1000
Rodolfo Rodrigo | 500 | 1978-11-23 | Traveling Expenses | [5 empty] | 500
Narciso Ramos | 1250 | 1978-08-28 | Traveling Expenses | [5 empty] | 1250
Felipe Santillan | 1250 | 1978-02-28 | Traveling Expenses | [5 empty] | 1250
Sub-total | #REF! |  |  | 364710 | 435509.56 | 0 | 0 | 0 | 67600
Advances to Special Disbursing
Irmina B. Francisco (PR#2491) | 35000 | 2017-03-23 | cash advance to defray expenses for the conduct of the Pangasinan Digital Influences' Training March 24-25, 2017 at Capitol Reosrt Hotel, Ling. Pang. | 35000
Wilfreda Vicente | 22200 | 2017-03-17 | cash advance to defray expenses for the conduct of Job's Fair and capability Enhancement Training March 9, 15 & 23, 2017 | 22200
Mr. Ramon M. Morden | 30195 | 2017-03-06 | cash advance to defray expenses for the participation of prov'l Anti-Drugs Abuse Council (PADAC) in the prov'l Anti-Crime and Drugs Summit | 30195
Maria Luisa Amor-Elduayan | 130200 | 2017-03-15 | cash advance to defray expenses for Commemorative Program during the Agew n Pangasinan 2017 | 130200
Maria Luisa Amor-Elduayan | 392800 | 2017-03-15 | cash advance to defray expenses for the celebration of 10th Pangasinan Tourism & Trade Expo during the Pista'y Dayat 2017 | 392800
Dalisay A. Moya | 297425 | 2017-03-16 | cash advances to defray expenses for the various events relative to the conduct of the Pangasinan Umaani Expo 2017 April 1, 2017 | 297425
Marife P. Acerit | 475100 | 2017-03-17 | cash advance to defray expenses for the Limgas na Pangasinan 2017 | 475100
Marife P. Acerit | 240000 | 2017-03-17 | cash advance to defray expenses for the Celebration of Limgas na Pangasinan 2017 | 240000
Alex F. Ferrer | 45350 | 2017-03-17 | cash advance to defray expenses during the launching to the Mobile skills Training project | 45350
Ma. Richelle M. Raguindin | 13000 | 2017-03-17 | cash advance to defray expenses for the conduct of Capability Enhancement Training march 22, 2017 | 13000
Merle Carriaga | 96740 | 2017-03-20 | cash advance to defray various expenses for Pistay Dayat 2017 celebration & Plants and garden Exhibit and Bonsai Plant Exhibit April 2 - May 5, 2017 | 96740
Dr. Cielo E. Almoite (PR#2233, 3/15/2017) | 81000 | 2017-03-20 | cash advance expenses to be incurred during the conduct of 11th Buntis Congress Celebration at the Municpality of Asingan | 81000
Maria Virginia Jaile G. De Leon | 96050 | 2017-03-24 | cash advance supplies & mayterials accomodation of judges for use for the Parada na Luyag 2017 : Grand Cultural Parade April 5, 2017 | 96050
Ramon M. Morden | 35000 | 2017-03-24 | cash advance to defray expenses to Regional DRRm Summit March 29, 2017 | 35000
Emilio P. Samson, Jr. | 101000 | 2017-03-24 | pymt of cash advance for the Prov'l Women's Convention Maarch 22-23, 2017 at Sison Auditorium Lingayen Pangasinan | 101000
Orpheus M. Velasco (PR#2369, 3/16/2017) | 56840 | 2017-03-27 | cash advance for Agew Na Pangasinan 2017 celebration | 56840
Orpheus M. Velasco | 169800 | 2017-03-27 | cash advance for Umaani Expo 2017 celebration | 169800
Atty. Verna T. Nava-Perez | 305000 | 2017-03-29 | cash advance miscellaneous expenses for the Celebration of Agew Na Pangasinan | 305000
Mr. Ramon M. Morden | 76500 | 2017-03-29 | cash advance to be used in transporting scholars from their respective campuses to Sison Aud. April 1, 2017 | 76500
Irmina B. Francisco | 59125 | 2017-03-29 | cash advance of miscellaneous expenses in PGO April 7, 2017 | 59125
Maria Virginia Jaile G. De Leon | 97500 | 2017-02-16 | cash advance requirements for the Renewal of Marital Vows, Love Games for couples during the Employees Family day Feb. 14, 2017 |  | 97500
Maria Luisa A. Elduayan (PR#1045, 2/9/2017) | 11000 | 2017-02-22 | cash advance to defray expenses for the RX PLUS a lifestyle & sports program of ABS-CBN with nationwide coverage Feb. 28 -March 2, 2017 |  | 11000
Maria Luisa Amor-Elduayan | 80000 | 2017-02-28 | cash advance to defray expenses of production cost of Golgotha, Cultural Presentation |  | 80000
Evan Gladish P. Domalanta | 393600 | 2017-01-19 | cash advance for the renewal of Firearms Licenses of Firearms |  | 393600
Rodolfo M. Cortez | 30000 | 1997-04-10 | [6 empty] | 30000
Rodolfo M. Cortez | 20000 | 1996-06-20 | [6 empty] | 20000
Sub-total | 3390425 |  |  | 2758325 | 582100 | 0 | 0 | 0 | 50000
Advances for Operating Expenses
| #REF! | 2017-03-24 | Irmina B. Francisco - cash advance to defray expenses to be used during the Thanksgiving Mass in the Agew na Pangasinan April 5, 2017 | 50000
| #REF! | 2017-03-24 | Irmina B. Francisco - cash advance of financial assistance for cultural presentation to begiven to diff constituents of Province of Pangasinan | 100000
| #REF! | 2017-03-20 | Engr. Antonieta C. Delos Santos - cash advance to be used for the Preventive Maintenance of various Prov'l Buildings | 200000
| #REF! | 2017-03-02 | Atty. Nimrod S. Camba - cash advance of financial assistance for Sports activities, cultural presentations & medications | 300000
| #REF! | 2017-03-24 | Atty. Nimrod S. Camba - cash advance of financial assistance for cultural presentation to begiven to diff constituents of Province of Pangasinan | 200000
| #REF! | 2017-02-08 | Irmina B. Francisco - cash advance of miscellaneous expenses in the PGO |  | 50000
| 350000 | 2017-02-28 | Cristina J. Bumiltac- replenishment of cash advance in pymt of various foodstuff & other operational expenses for use at Capitol Resort Hotel, Feb. & mar. 2017 |  | 350000
| 95000 | 2017-01-20 | Edwin B. Sison - cash advance for pymt of annual registration fees of various motor vehicle with plate numbers ending (2) & (3) |  | 95000
Sub-total | #REF! |  |  | 850000 | 495000 | 0 | 0 | 0 | 0
GRAND TOTAL | #REF! |  |  | 3973035 | 1512609.56 |  |  |  | 117600
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
CATHERINE DC. CAMBA, CPA |  |  |  |  | HON. AMADO I. ESPINO, III
Officer in Charge-Provincial Accounting Office |  |  |  |  | Governor