## 4thQTR2013 (hidden)
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th QUARTER, CY 2013
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Asphalt and Pre-Mix for Buenlag Provincial Road, San Isidro Norte Section, Binmaley | San Isidro Norte Section, Binmaley | 1190433 |  |  | 100% | 1190433 |  | Paid on Oct., 2013 | 6911 | Exponential Headway Real Estate Dev't Corp
Concreting of Brgy. Tombor Rd. I & II, | Binmaley, Pangasinan | 1197506.68 |  |  | 100% | 1197506.68 |  | Paid on Oct., 2013 | 6911 | KJRS Construction Enterprises
Renovation of existing supply and storage bldg., into medical supply bldg | Eastern Pang. Dist. Hospital, Tayug | 410331.23 |  |  | 100% | 410331.23 |  | Paid on 12/20/13 | 6911 | BET Const'n
Replacement of G.I. furnaces for parts, repair of damaged concrete floor slab at Capitol Bldg., | Capitol Bldg., | 68574 |  |  | 100% | 68574 |  | Controlled dtd 11/2013 | 3917 | EPHRAH Entp
Improvement of Brgy. Hall | Matalava, Lingayen, Pangasinan | 301785.96 |  |  | 100% | 301785.96 |  | Controlled dtd 11/2013 | 3917 | MCB Const'n & Supply
Construction of concrete Canal with removable cover | along Castillo-Maniboc Road, Maniboc, Lingayen | 611700.77 |  |  | 100% | 611700.77 |  | Controlled dtd 11/2013 | 3917 | BET Const'n & Supply
additional works for the construction of Nipa Shed Waiting Area, Phase 2, | Mapandan Community Hospital | 85517.3 |  |  | 100% | 85517.3 |  | Controlled dtd 12/2013 | 3917 | ALCEL Const'n
Installtion of automatic transfer switch | Manaoag Com. Hospital | 139737.5 |  |  | 100% | 139737.5 |  | Controlled dtd 11/2013 | 3917 | ZOTA Trdg. & Const'n
Construction of 2 units - 6 cubicles temporary comfort rooms for men and women with water system | at Bical Sur, Bayambang, Pangasinan | 159929 |  |  | 100% | 159929 |  | Controlled dtd 11/2013 | 3917 | W.M. Salayog
Construction of Drainage Canal | PPH, Bolingit, San Carlos, Pangasinan | 2240472.56 |  |  | 100% | 2240472.56 |  | Controlled dtd 11/2013 | 3917 | Lucky G18 Const'n
fabrication and installation of reflectorize signboard for Highway curves | Along Urdaneta-Asingan Rd., via Calepan Provincial Road, Asingan | 85444.4 |  |  | 100% | 85444.4 |  | Controlled 11-2013 | 8917-1 | W.M. Salayog
Improvement/blocktopping of Pob. East (Pandayan St.,) Calasiao | Pob. East (Pandayan St.,) Calasiao | 347580 |  |  | 100% | 347580 |  | Controlled 12-2013 | 8917-1 | Exponential Headway Real Estate Dev't Corp
Economic Development
improvement/asphalting/patching of San Manuel - San Nicolas, San Vicente Section | San Manuel, Pangasinan | 2384670 |  |  | 100% | 2384670 |  | Controlled 11-2013 | 8917-1 | Exponential Headwa
Blocktopping of Polong Road | Bugallon, Pangasinan | 414427.5 |  |  | 100% | 414427.5 |  | Controlled 11-2013 | 8917-1 | Exponential Headwa
Concreting of San Isidro Sur Road | Binmaley, Pangasinan | 228983.79 |  |  | 100% | 228983.79 |  | Controlled 11-2013 | 8917-1
Blocktopping of Pangapisan Sur Road | Lingayen, Pangasinan | 1912646 |  |  | 100% | 1912646 |  | Controlled 10-2013 | 8917-1 | Zota Trdg
Repair/rehab of 1- Barrel RCBC along Boboy-Abagatanen Rd., | Poblacion , Agno, Pangasinan | 80686 |  |  | 100% | 80686 |  | Controlled 10-2013 | 8917-1 | Safeway Const'n
Repair/rehab of damaged sub & super structure of Bisclac Bridge | San Manuel, Pangasinan | 447140.8 |  |  | 100% | 447140.8 |  | Controlled 12-2013 | 8917-1 | Zota Trdg
Riprapping of Banaga Bridge Riverbank | Brgy. Banaga, Bugallon, Pangasinan | 874124.04 |  |  | 100% | 874124.04 |  | Controlled 12-2013 | 8917-1 | KJRS Const'n
Asphalting works infront of the Building at headquarters Regional Maritime Unit - 1 | Dagupan City, Pangasinan | 220405 |  |  | 100% | 220405 |  | Controlled 12-2013 | 8917-1 | Exponential Headwa

## 1stQTR2014 (hidden)
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER, CY 2014
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
concreting of Brgy. Portic Rd., | Bugallon, Pangasinan | 1255794.61 |  |  | 100% | 1255794.61 |  | Controlled 3-17-14 | 6911 | W.M. Salayog Const'n & Gen. Mdse PR# 0253
rehabilitation/improvement of Main Building (completion of Module and Right Wing) @ EPDH, | Tayug, Pangasinan | 5262605.08 |  |  | 60% | 3157563.05 |  | 100% Completed on April, 2014 | 6911 | BET Contruction & Supply
construction of CHB Drainage Canal, Installation/Fabrication of concrete cover of existing drainage canal | Limahong St., San Pedro West, Rosales, Pangasinan | 703605.31 |  |  | 100% | 703605.31 |  | Controlled 3-27-14 | 3917 | Maricris Entp
construction of Bislac Bridge, | San Manuel, Pangasinan | 746672.64 |  |  | 100% | 746672.64 |  | Obligated March-2014 | 3917 | MCB Constn & Supply
Economic Development
concreting of Balungao-Napudot Rd. (Phase II) | Balungao, Pangasinan | 1920946.26 |  |  | 100% | 1920946.26 |  | Obligated 3-2014 | 8917-1 | Safeway Construction and Supply

## 2ndQTR2014 (hidden)
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER, CY 2014
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Rehabilitation/improvement of Main Building (completion of Module and Right Wing) @ EPDH, Tayug, Pangasinan | Bugallon, Pangasinan | 5262605.08 |  |  | 100% | 5262605.08 |  | 100% Completed on April, 2014 | 6911 | BET Contruction & Supply
Rehabilitation/improvement of Main Building (completion of Module and Right Wing) @ EPDH, | Tayug, Pangasinan | 5262605.08 |  |  | 100% | 3157563.05 |  | 100% Completed on April, 2014 | 6911 | BET Contruction & Supply
Improvement/rehabilitation of Auditorium with stage at Bani Municipal Plaza | Bani, Pangasinan | 2038013.12 |  |  | 100% | 2038013.12 |  | 100% Completed on April, 2014 | 6911 | Alcel Constn.
Rehabilitation of Burgos Municipal Gymnasium, Gov't Service Center | Burgos, Pangasinan | 2247848.91 |  |  | 100% | 2247848.91 |  | 100% Completed on 5-15-14 | 6911 | Safeway Constn PR# 1745
Construction of Additional 2-Span covered court of Brgy. Bañaga | Bugallon, Pangasinan | 726995.3 |  |  | 100% | 726995.3 |  | 100% Completed on 4-28-14 | 6911 | W.M. Salayog PR# 1522
Improvement/repair of Perimeter Fence, Brgy. Bobonot, Dasol Breeding Station | Dasol, Pangasinan | 668809.9 |  |  | 100% | 668809.9 |  | 100% Completed on 6-20-14 | 6911 | ALCEL Const. PR# 1894
CONSTRUCTION of GIRL SCOUT BLDG., PHASE II | Lingayen, Pangasinan | 1816784.25 |  |  | 100% | 1816784.25 |  | 100% Completed on 5-15-14 | 6911 | BET Constn PR#0591
CONSTRUCTION of BOY SCOUT BLDG., PHASE II | Lingayen, Pangasinan | 1896815.43 |  |  | 100% | 1896815.43 |  | Controlled 5-15-14 | 6911 | BET Constn PR#0676
INSTALLATION OF 3-167 KVA Transformer at EPDH | TAYUG, Pangasinan | 5404767.19 |  |  | 100% | 5404767.19 |  | 100% Completed on 6-5-14 | 6911 | W.M. SALAYOG Constn.PR#2079
FABRICATION AND INSTALLATION OF STEEL COVER AND CONCRETE CANAL AT BUGALLON PUBLIC MARKET | Bugallon, Pangasinan | 677499.48 |  |  | 100% | 677499.48 |  | 100% Completed on 5-15-14 | 6911 | W.M. SALAYOG Constn PR#2278
Repair/improvement of covered court; construction of CR at Pangasian Prov'l Hosp | San Carlos, Pangasinan | 1726214.48 |  |  | 100% | 1726214.48 |  | 100% Completed on 5-15-14 | 6911 | KJRS Const'n Entp.PR#1733
Improvement of Old Public Market Bldg., "B", at Bugallon Public Market | Bugallon, Pangasinan | 9095383.79 |  |  | 50% | 4548191.89 |  | 100% Completed on 6-20-14 | 6911 | Bet Constn PR#2193
Repainting of bridges in the 5th and 6th PED | 5th and 6th PED | 245194 |  |  | 100% | 245194 |  | 100% Completed on 6-20-14 | 8917-1 | NBL ENTP. PR# 2894
Concreting of Bued-Ambonao Road | Calasiao, Pangasinan | 538772 |  |  | 100% | 538772 |  | 100% Completed on 6-20-14 | 8917-1 | MCB Constn PR# 2486
Repair of Prof. Amado G. Espino, Sr. MP Gymnasium | Bugallon, Pangasinan | 24448 |  |  | 100% | 24448 |  | 100% Completed on 4-25-14 | 3917 | NBL ENTP. PR# 0551
Siphoning/cleaning of various septic tanks @ various Prov'l Govt. Hospitals Bldgs and portalets | various Prov'l Govt. Hospitals Bldgs and portalets | 154492 |  |  | 100% | 154492 |  | 100% Completed on 6-20-14 | 3917 | SAFEWAY Const. PR# 1168
Repair of ALS Bldg., (Male and Female CR) at Brgy. Portic | Brgy. Portic, Bugallon, Pangasinan | 71821 |  |  | 100% | 71821 |  | 100% Completed on 5-14-14 | 3917 | W.M. Salayog ConstnPR# 1592
Concreting of Lingayen Fire Station Office Flooring and Parking Area | Lingayen, Pangasinan | 638780.41 |  |  | 100% | 638780.41 |  | 100% Completed on 4-28-14 | 3917 | W.M. Salayog Constn PR#0368
Repair and Maintenance of 3 Gensets at NRSCC, Sison Auditorium and Capitol Bldg | NRSCC, SISON AUDITORIUM AND CAPITOL BLDG. | 119000 |  |  | 100% | 119000 |  | 100% Completed on 6-19-14 | 3917 | Alma S. Macaranas Trdg. PR#0378
Improvement/repair of COMELEC Prov'l Supervisor's Off., Astrodome, Dagupan City | Dagupan City | 609572.9 |  |  | 100% | 609572.9 |  | 100% Completed on 4-29-14 | 3917 | MCB CONSTN. PR#0378
Improvement/Asphalting of Capitol Loop, Capitol Compound | Capitol Compound, Lingayen, Pangasinan | 444159 |  |  | 100% | 444159 |  | 100% Completed on 6-3-14 | 3917 | Exponential Headway Real Estate PR#0509
Installation of Feederline Underground Electric Wiring and Supply Wiring Generator Set | Urdaneta Dist. Hosp., Urdaneta City | 380862.5 |  |  | 100% | 380862.5 |  | 100% Completed on 6-20-14 | 3917 | LUCKY G18 CONST. PR#2151
Improvement/Rehabilitation of Center for Excellence of Employee Devt, Kalantiao Bldg | Capitol Compound, Lingayen, Pangasinan | 527350 |  |  | 100% | 527350 |  | 100% Completed on 5-14-14 | 3917 | W.M. Salayog PR#2179
Construction of Perimeter fence with Grills and repair/extension of Brgy. Outpost | Brgy. Portic, Bugallon,Pangasinan | 542085.07 |  |  | 100% | 542085.07 |  | 100% Completed on 6-20-14
Economic Development
Construction of Additional Communal Irrigation System/Dam at Brgy. Hacienda | Bugallon, Pangasinan | 1627226.74 |  |  | 100% | 1627226.74 |  | 100% Completed on 6-5-14 | 8911 | KJRS Const'n. Entp. PR# 1551
Blocktopping of Barangay road | Alaminos City | 6416046 |  |  | 100% | 6416046 |  | 100% Completed on 4-25-14 | 8917-1 | Exponential Headway PR# 0296
improvement (riprapping) of side slope of Brgy. Road, Brgy. Dupo | Binmaley, Pangasinan | 10352790 |  |  | 50% | 5166175.09 |  | Controlled 5-15-14 | 6911 | BET Contruction & Supply
Ground improvement (concreting at Bugallon Public Market) | Bugallon, Pangasinan | 6170862.64 |  |  | 100% | 6170862.64 |  | 100% Completed on 4-21-14 | 3917 | MCB Constn & Supply
Concreting of Brgy. Umanday Road, (Sitio Cupang) with grouted riprap at Brgy. Umanday | Bugallon, Pangasinan | 3060644 |  |  | 60% | 1836386.4 |  | Controlled 5-20-14 | 8917-1 | BET Constn & Supply PR# 1965
Asphalting/blocktopping of Bical Sur Road, w/ slope protection(extension) Bical Sur, Bayambang, Pangasinan | Bayambang, Pangasinan | 3260595 |  |  | 100% | 3260595 |  | 100% Completed on 5-27-14 | 8917-1 | Exponential Headway PR# 1964
Asphalting/blocktopping of various streets | Bolinao, Pangasinan | 5674884 |  |  | 100% | 5674884 |  | 100% Completed on 5-29-14 | 8917-1 | Exponential Headway PR# 1895
Asphalting of Bical Road (North and Sur) | Bayambang, Pangasinan | 4386005 |  |  | 100% | 4386005 |  | 100% Completed on 5-27-14 | 8917-1 | Exponential Headway PR# 139
IMPROVEMENT/REHABILITATION OF NILOMBOT BRIDGE | MAPANDAN, Pangasinan | 2353633.31 |  |  | 100% | 2353633.31 |  | 100% Completed on 6-5-14 | 8917-1 | MCB Constn.PR# 2862
Blocktopping at Magsaysay Road | Alaminos City | 2523372 |  |  | 100% | 2523372 |  | 100% Completed on 4-25-14 | 8917-1 | Exponential Headway PR# 0296
Payment of Loan Amortization | Land Bank of the Philippines | 64225751.5 |  |  |  | 64225751.5
Environmental Development
Preparation/landfill/backfilling of Brgy. Road, Dupo and Waste Disposal of Dredging Machine | Binmaley, Pangasinan | 459497.5 |  |  | 100% | 459497.5 |  | 100% Completed on 4-28-14 | 8912-1 | EPHRAH ENT., PR# 0906

## 3rdQTR (hidden)
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 3RD QUARTER, CY 2014
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Construction of 2-storey ABC Bldg., | Lingayen, Pangasinan | 17083000 |  |  | 100% | 17083000 |  | Controlled 9-23-14 |  | 6911 | CAD Const.PR# 1769
Construction of Brgy. Hall, Brgy. Basing, | Lingayen, Pangasinan | 888375.92 |  |  | 100% | 888375.92 |  | Paid 7-2014 |  | 6911 | W.M. Salayog PR# 1085
Repair of PSWDO Office and Child Care Development Center (CCDC) | Lingayen, Pangasinan | 1623474.32 |  |  | 100% | 1623474.32 |  | Paid in 7-2014 |  | 6911 | Lucky G18 PR#2703
Completion of Brgy. Hall at Salasa | Bugallon, Pangasinan | 1737238.02 |  |  | 100% | 1737238.02 |  | Paid in 7-2014 |  | 6911 | W.M. SALAYOG Const PR#2133
Concreting of Brgy. Umanday Road, (Sitio Cupang) with grouted riprap at Brgy. Umanday, | Bugallon, Pangasinan | 3060644 |  |  | 100% | 3060644 |  | Paid 7-2014 |  | 8917-1 | BET Constn & Supply PR# 1965
Painting of various steel bridges within 4th-6th District | 4th-6th District | 167746 |  |  | 100% | 167746 |  | Controlled 9-4-14 |  | 8917-1 | Ephrah Entp PR# 3639
Fees for Geological Site Scooping, Eng'g Geologic and Geohazard Assessment and Review of Initial Environmental Examination for the issuance of Environmental Compliance Certificate of Aplaya West Resettlement and Estuario Grande Village Project | Lingayen, Pangasinan | 120000 |  |  | 100% | 120000 |  | Paid 8-2014 | 6511-1 | Engr. Alvin L. Bigay PR# 5575
Construction of water system in Bañaga | Bugallon, Pangasinan | 145125 |  |  | 100% | 145125 |  | 100% as of Oct., 2014 | 8919-2 | Safeway Constn. PR#2493
Maintenance of water and sewer system around Capitol Compound | Lingayen, Pangasinan | 104175 |  |  | 100% | 104175 |  | Controlled 9-23-14 |  | 8919-2 | PR#1364
Construction of 2 units deepwells | Sitio Centro, Brgy. Mabini, Balungao, Pangasinan | 117950 |  |  | - | 117950 |  | Obligated |  | 8919-2 | PR#6625
Replacement of submersible pump at Capitol Water System, Capitol Compound | Lingayen, Pangasinan | 196595 |  |  | - | 196595 |  | Obligated |  | 8919-2 | PR#7331
Construction of 3 (u) Artesian Well | Yatyat, Turco, Nambagatan, Laoac, Pangasinan | 259039 |  |  | - | 259039 |  | Obligated |  | 8919-2 | PR#8040
Installation and tapping of Water System Distribution Pipeline at Mangatarem Dist. Hosp. | Mangatarem, Pangasinan | 25065 |  |  | - | 25065 |  | Obligated |  | 8919-2 | PR#8135
Installation of Water Treatment at ICU Dialysis At Pang. Prov'l Hosp. | San Carlos City | 740254 |  |  | - | 740254 |  | Obligated |  | 8919-2 | PR#7996
Construction of deepwell (Level 1) Artesian Well Project (200 depth) | Warey, Malasiqui, Pangasinan | 221610 |  |  | - | 221610 |  | Obligated |  | 8919-2 | PR#7789
General Repair of Alaminos Police Station | Alaminos City | 489153.38 |  |  | 100% | 489153.38 |  | Controlled 7-9-14 |  | 3917 | Zota Trdg. PR#1012
1 set panel mtrs 600A 3P for temporary installation of Generator set at Tayug District Hospital | Tayug, Pangasinan | 120425 |  |  | 100% | 120425 |  | Controlled 7-31-14 |  | 3917 | W.M. Salayog PR#2538
Construction of Perimeter fence with Iron Grills and Steel Gate at Pangapisan Sur E/S | Lingayen, Pangasinan | 391026.08 |  |  | 100% | 391026.08 |  | Controlled 7-10-14 |  | 3917 | Lucky G18 PR#2289
Feederline underground installation and relocation of generator set and transformer and upgrading transformer | Pozorrubio Community Hospital | 384706 |  |  | 100% | 384706 |  | Controlled 8-1-14 |  | 3917 | Safeway Const. PR#2537
Siphoning/cleaning of various septic tank at Veteran's Park, Canteen front of Motorpool, Lingayen & Capitol Resort | Lingayen, and various Prov'l Hospitals around Pangasinan | 273000 |  |  | 100% | 273000 |  | Controlled 8-8-14 |  | 3917 | NBL Entp. PR#4624
Asphalting of Drainage & Parking Area of CENRO | Tondaligan, Dagupan City | 367464 |  |  | 100% | 367464 |  | Controlled 9-23-14 |  | 3917 | Exponential Headway PR#5166
Repair/Restoration of Bengzon-Yuson Residential Bldg.,(Phase I) | Lingayen, Pangasinan | 4989393.42 |  |  | 100% | 4989393.42 |  | Controlled 9-23-14 |  | 3917 | Safeway Constn. PR#5637
Repair/improvement of United Way Bldg., (Main Bldg., Phase II,) | Lingayen, Pangasinan | 4773795.13 |  |  | 100% | 4773795.13 |  | Controlled 9-23-14 |  | 3917 | BET Constn PR#4254
Installation of Underground Feederline Wiring from Electrical Room, Main Bldg., to Generator House @ EPDH | Tayug, Pangasinan | 4491066.52 |  |  | 100% | 4491066.52 |  | Controlled 9-23-14 |  | 3917 | W.M. Salayog PR#2680
Repair/improvement of United Way Annex Bldg., Phase II | Lingayen, Pangasinan | 1097268.91 |  |  | 50% | 1097268.91 |  | Controlled 8-26-14 |  | 3917 | BET Constn. PR#3470
Construction of generator house @ Motorpool compound | Lingayen, Pangasinan | 260415 |  |  | - |  |  | Obligated |  | 3917 | W.M. Salayog PR#6286
Construction of generator house @ Finance Bldg. | Lingayen, Pangasinan | 245590.14 |  |  | 100% | 245590.14 |  | Controlled 10-9-14 |  | 3917 | W.M. Salayog PR#6286
Construction of generator house @ Kalantiao Bldg. | Lingayen, Pangasinan | 322644.5 |  |  | 100% | 322644.5 |  | Controlled 10-9-14 |  | 3917 | Zota Trdg. PR#6870
Construction of perimeter fence, catch basin, line canal with steel cover & add'l CHB wall of the existing perimeter fence @ Slaughter house | Socony, Bugallon, Pangasinan | 724572 |  |  |  | 724572 |  | Obligated |  | 3917 | PR#6664
Construction of deepwell (Level 1) Artesian Well Project (200 depth) | Cabanaetan, Mabini, Pangasinan | 268634 |  |  |  | 268634 |  | Obligated |  | 8919-2 | PR#7881
Construction of deepwell (Level 1) Artesian Well Project (160 ft depth) at | Gais-Guipe, Dasol, Pangasinan | 213068 |  |  |  | 213068 |  | Obligated |  | 8919-2 | PR#8019
Construction of 1 (u) deepwell, | Brgy. Quetegan, Mangatarem, Pangasinan | 133546.47 |  |  |  | 133546.47 |  | Obligated |  | 8919-2 | PR#7675
Replacement and extension of water system | Brgy. Estanza, Lingayen, Pangasinan | 128868 | [5 empty] | Obligated |  | 3917 | PR#4374
Fabrication/installation of Steel grills of existing perimeter fence @ WPDH | Alaminos City, Pangasinan | 312807.36 |  |  | 100% | 312807.36 |  | Controlled 10-9-14 |  | 3917 | Zota Trdg. PR#6774
Economic Development
Repair/rehabilitation of Repair Bay No. 1 and Office Bldg., Motorpool Compound | Lingayen, Pangasinan | 7301053.42 |  |  | 40% | 2918323.92 |  | Controlled 9-23-14 |  | 6911 | Safeway Const. & Supply PR#1595
Repainting of various provincial bridges around Pangasinan | Pangasinan | 175779 |  |  | 100% | 175779 |  | Controlled 8-20-14 |  | 8917-1 | Ephrah Ent. PR# 0569
Asphalting and blocktopping of Tulong West Road, | Urdaneta, Pangasinan | 2719475 |  |  | 100% | 2719475 |  | Controlled 9-23-14 |  | 8917-1 | Exponential Headway PR# 1680
Concreting of Brgy. Domalandan East Road., | Lingayen, Pangasinan | 496874.14 |  |  | 100% | 496874.14 |  | Controlled 8-20-14 |  | 8917-1 | Zota Trdg. PR# 0934
Feeder Road, Brgy. Naguilayan | Binmaley, Pangasinan | 2750508.12 |  |  | 100% | 2750508.12 |  | Paid 7-2014 |  | 8917-1 | ZOTA TRDG. PR# 2273
Concreting of Mapandan-Banaoang Road, | Sta. Barbara, Pangasinan | 385032.48 |  |  | 100% | 385032.48 |  | Paid 7-2014 |  | 8917-1 | ZOTA TRDG PR# 2440
Blocktopping of Mapandan-Pias Rd. and Mapandan-Manaoag Rd., | Mapandan, Pang. | 358180 |  |  | 100% | 358180 |  | Paid 7-2014 |  | 8917-1 | Exponential Headway PR# 2539
Concreting of Cabarabuan-Lawak-Langka Road, | Mangatarem, Pangasinan | 1796634 |  |  | 15% | 268819.8 |  | Controlled 9-23-14 |  | 8917-1 | Safeway Constn PR# 1941
Blocktopping/patching along San Jacinto-Pozorrubio Road, Lobong Section, | San Jacinto, Pangasinan | 1103100 |  |  | 100% | 1101771 |  | Controlled 9-3-14 |  | 8917-1 | Exponential Headway PR# 1746
Concreting of Quetegan-Bunlalacao Road, | Mangatarem, Pangasinan | 8005394 |  |  | 15% | 1199516.31 |  | Controlled 9-23-14 |  | 8917-1 | Zota Trdg. PR# 1896
Concreting of Rajal-Esmeralda Road | Balungao, Pangasinan | 11250114.59 |  |  | 15% | 1685928.42 |  | Controlled 9-23-14 |  | 8917-1 | BET Constn PR# 2536
Asphalting the Parking Area, Poblacion, | Lingayen, Pangasinan | 1688472 |  |  | 100% | 1688472 |  | Controlled 8-22-14 |  | 8917-1 | Exponential Headway PR#4255
Asphalting/Blocktopping of Baybay Polong Rd., | Binmaley, Pangasinan | 2613768 |  |  | 100% | 2613768 |  | Controlled 8-22-14 |  | 8917-1 | Exponential Headway PR#4209
Improvement/Asphalting of Road going to Baywalk, Capitol Compound | Lingayen, Pangasinan | 1542274 |  |  | 100% | 1542274 |  | Controlled 8-22-14 |  | 8917-1 | Exponential Headway PR#5233
Blocktopping/asphalting of Brgys. Poblacion West and San Antonio Road | Sto. Tomas, Pangasinan | 6186218 |  |  | 100% | 6186218 |  | Controlled 8-22-14 | 8917-1 | Exponential Headway PR#6341
Concreting of Ketegan-Palisoc Rd., | Bautista, Pangasinan | 3351760 |  |  | 100% | 3351760 |  | Controlled 9-23-14 | 8917-1 | ZOTA Trdg. PR#2597
Construction of roofing of 2 units pathway of Public Market, | Bugallon, Pangasinan | 3256232 |  |  | 40% | 1300200.4 |  | Controlled 9-24-14 |  | 6911 | Zota Trdg.
Improvement of Old Public Market Bldg., "B", at Bugallon Public Market | Bugallon, Pangasinan | 9096383.79 |  |  | 100% | 9096383.79 |  | Controlled 9-23-14 |  | 6911 | BET Constn. PR#2193
Asphalting of various provincial roads | Pangasinan | 72705 |  |  | 100% | 72705 |  | Controlled 8-13-14 |  | 8917-1 | Ephrah Ent. PR# 1749
Improvement of stairs, view deck and completion of CR#2 @ Governor's Island, Lucap | Alaminos City, Pangasinan | 363206.13 |  |  | 100% | 363206.13 |  | Controlled 10-9-14 |  | 3917 | Lucky G18 PR#6618
Repair of CR fixtures and facilities at Governor's Island, Lucap | Alaminos, Pangasinan | 416293 | [5 empty] | Obligated |  | 3917 | PR#4321
Improvement of Bathhouse at Beachfront, Capitol | Lingayen, Pangasinan | 244403 |  |  | 100% | 244403 |  | Controlled 7-31-14 |  | 3917 | MCB Constn. PR#4197
Improvement (riprapping) of side slope of Brgy. Road, | Brgy. Dupo, Binmaley, Pangasinan | 10332350.18 |  |  | 80% | 8265880.14 |  | Controlled 8-6-14 |  | 6911 | BET Const. PR# 1836
Construction of Communal Irrigation System/Dam @ Sitio Samat, Brgy. Hacienda, | Bugallon, Pangasinan | 463843.23 |  |  | 100% | 463843.23 |  | Controlled 8-20-14 |  | 8911 | KJRS Constn PR# 4264
Construction of Irrigation Canal w/ Riprap, Brgy. Hacienda, | Bugallon, Pangasinan | 1623112 |  |  | 50% | 807586.72 |  | Controlled 7-31-14 |  | 8911 | BET Const. PR# 5370
15500 pcs empty sacks of rice for preparation wasted disposal of dredging machine at Brgy. Dupo, | Binmaley, Pangasinan | 186000 |  |  |  | - |  | Obligated |  | 8912-4 | PR#7334
various spare parts for use of dredging machine #2 |  | 1276500 | [5 empty] | Obligated |  | 8912-4 | PR#7383
Lauro G. Caoile/Salome Q. dela Peña - Loan granted to Bantay Bayan Association |  | 150000 |  |  | 100% | 150000 |  | Paid 8-2014 |  | 8915
Arturo M. Co/Ana M. Pahela - Loan granted to Golden Mountain MPC |  | 150000 |  |  | 100% | 150000 |  | Paid 8-2014 |  | 8915
Anna Liza C. Obana/Elvira D. Tomas - Loan granted to Lucky Rooster Consumer's Coop. |  | 150000 |  |  | 100% | 150000 |  | Paid 8-2014 |  | 8915
Arturo B. Cariño - Loan granted to Anda SEA-K MPC |  | 150000 |  |  | 100% | 150000 |  | Paid 8-2014 |  | 8915
Payment of Loan Amortization | Land Bank of the Philippines | 96424511.24 |  |  |  | 96424511.24 |  | Paid as of Sept, 2014
Environmental Development
Forest tree seeds, and other various materials needed for the propagation of fruit and forest tree seedlings at the field stations | Sta. Barbara, San Quintin, Mangatarem and Lingayen | 299400 | [5 empty] | Obligated |  | 8919 | PR#7173
300 coconut seedlings for Tree Planting at Capitol Beachfront, Baywalf Area | Lingayen, Pangasinan | 45000 | [5 empty] | Obligated |  | 8919 | PR#7657

## 20%IRA
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th QUARTER, CY 2014
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
fabrication of 2 units drilling rig for drilling of Artesian Well | Around Pangasinan | 459548 | [5 empty] | Obligated |  | PR#9710 | 6911
Rehabilitation of Provincial Library Bldg., | Capitol, Lingayen, Pangasinan | 1322823.96 | 2014-11-30 | 2015-01-08 | 100% | 1322823.96 |  | Paid in 12-2014 |  | MCB Constn. PR#5424
Completion of mezzanine of covered court | Brgy., Malimpuec, Lingayen, Pangasinan | 1157760 | 2014-11-30 | 2014-12-15 | 100% | 1157760 |  | Paid in 12-2014 |  | Zota Trdg., PR#10861 | 6911
Additional works for repair/improvement of Public Auditorium, Pob., Burgos, Pangasinan | Poblacion, Burgos, Pangasinan | 1704371 | 2014-11-28 | 2015-01-15 | 100% | 934464.84 |  | Controlled 12-11-14 |  | BET Constn. PR#10612 | 6911
Construction of Line Canal w/ concrete cover | Brgy. Matalava, Lingayen, Pangasinan | 657726.14 | 2014-11-30 | 2014-12-29 | 100% | 657726.14 |  | Paid in 12-2014 |  | W.M. Salayog PR#10612 | 6911
General repair of PNP Station, | Poblacion, Bani, Pangasinan | 538210 | 2014-12-26 | 2015-01-16 | 100% | 538210 |  | Obligated |  | PR#5568 | 6911
Construction of Tourism Information Center, Lingayen Beachfront | Lingayen, Pangasinan | 2624121 | 2014-05-27 | 2014-07-17 | (For Bidding) |  |  | Obligated |  | PR#6098 | 6911
Repair/restoration of Bengzon-Yuzon Bldg., at Bengzon St., Phase 2 | Lingayen, Pangasinan | 4900000 | 2014-05-27 | 2014-07-17 | (For Bidding) |  |  | Obligated |  | PR#10821 | 6911
Repair/improvement of perimeter fence/lightings at WPDH | Alaminos City | 438152.47 | 2013-10-25 | 2014-06-05 | 100% |  |  | Paid in 12-2014 |  | Alcel Constn PR#6100 | 6911
Construction/rehabilitation of various support facilities | Pozorrubio, Pangasinan | 2225618.21 | 2012-09-24 | 2013-07-09 | 100% |  |  | Paid in 12-2014 |  | Accuracy Builders PR#5214 | 6911
Construction of 2 units Geriatic Ward Male and Female, Construction of 2 units Public Comfort Room with Septic Tanks and Construction of Ramp | WPDH, Alaminos City | 560411.4 | 2011-12-23 | 2012-08-24 | 100% | 560411.4 |  | Paid in 12-2014 |  | BET Constn. PR#13236 | 6911
Construction of Drainage Canal and Peripheral Lightings at Bayambang Dist. Hosp., | Bayambang, Pangasinan | 262742.39 | 2014-03-31 | 2014-05-16 | 100% | 262742.39 |  | Paid in 12-2014 |  | KJRS Constn. PR#13262 | 6911
Asphalting of Access Road at TESDA, | Lingayen, Pangasinan | 342300 | 2014-08-12 | 2014-08-12 | 100% |  |  | Obligated
REHABILITATION of AMADO ESPINO, SR. GYMNASIUM |  | 281206.27 |  |  | 100% | 281206.27 |  | Paid 11/2014 |  | 3917 | W.M. Salayog PR#2305
REHABILITATION OF COGON HOUSE AT OPAG FIELD OFFICE | BRGY. SAN GONZALO, SAN QUINTIN, PANGASINAN | 362329.8 | 2014-03-05 | 2014-04-10 | 100% | 362329.8 |  | Paid 10/2014 |  | 3917 | KJRS Constn PR#2293
Improvement/repair of various facilities at Dasol Community Hospital | Dasol, Pangasinan | 384373.2 | 2013-02-24 | 2014-04-24 | 100% | 384373.2 |  | Paid 10/2014 |  | 3917 | Zota Trdg. PR#2002
Repair of CR fixtures and facilities at Governor's Island, Lucap, | Alaminos, Pangasinan | 413730.12 | 2014-04-21 | 2014-06-14 | 100% |  |  | Paid 12/2014 |  | 3917 | Zota Trdg. PR#4321
provision of water system at Sitio Babaliwan, | Brgy. Namolan, Lingayen, Pangasinan | 78415 |  |  | 100% | 78415 |  | Paid 12/2014 |  | 3917 | W.M. Salayog PR#5599
1 unit 1.5 SAER motor pump & gauge pressure switch, 1 unit 1.0 HP US goulds centrifugal w/ gauge pressure switch for Bahay Pag-asa | Lingayen, Pangasinan | 46500 |  |  | 100% | 46500 |  | Paid 11/2014 |  | 3917 | PR#5258
various materials- proposed stone masonry with concrete barrier along Mabilao-Banday Rd., San Fabian, Pangasinan |  | 156693 | 2014-09-22 | 2014-12-02 | 100% | 156693 |  | Paid 12/2014 |  | 3917 | Zota Trdg., PR#2629
Construction of generator house @ Motorpool compound | Lingayen, Pangasinan | 258781.12 | 2014-09-07 | 2014-10-10 | 100% | 258781.12 |  | Paid 10/2014 |  | 3917 | PR#6606
Construction of generator house @ Finance Bldg. | Lingayen, Pangasinan | 245590.14 | 2014-08-03 | 2014-10-10 | 100% |  |  | Paid 10/2014 |  | 3917 | W.M. Salayog PR#6286
Construction of generator house @ Kalantiao Bldg. | Lingayen, Pangasinan | 322644.5 | 2014-08-03 | 2014-10-10 | 100% |  |  | Paid 10/2014 |  | 3917 | Zota Trdg. PR#6870
construction of perimeter fence, catch basin, line canal with steel cover & add'l CHB wall of the existing perimeter fence @ Slaughter house, | Socony, Bugallon, Pangasinan | 721255.93 | 2014-10-27 | 2014-11-27 | 100% | 721255.93 |  | Paid 11/2014 |  | 3917 | W.M. Salayog PR#6664
Fabrication/installation of Steel grills of existing perimeter fence | WPDH, Alaminos City | 312807.36 | 2014-08-28 | 2014-09-17 | 100% | 312807.36 |  | Paid 10/2014 |  | 3917 | Zota Trdg. PR#6774
Improvement of stairs, view deck and completion of CR#2 @ Governor's Island | Lucap, Alaminos City, Pangasinan | 363206.13 | 2014-04-21 | 2014-06-14 | 100% | 363206.13 |  | Paid 10/2014 |  | 3917 | Lucky G18 PR#6618
const'n of 2 units deepwell, (D180 ft) at Sitio Centro | Brgy., Mabini, Balungao, Pangasinan | 37880 | For Bidding |  |  |  |  | Obligated |  | 3917 | PR# 10735
Installation of Generator Set ATS Panel | Kalantiao Bldg., Lingayen, Pang. | 982486 | [5 empty] | Obligated |  | 3917 | PR# 10685
Installation of Generator Set ATS Panel | Finance Bldg., Lingayen, Pang. | 1219416 | [5 empty] | Obligated |  | 3917 | PR# 10714
Additional repair of 2 existing Bldg. and Ground Floor Improvement at the back of Cattle Shed, | Brgy. Socony, Bugallon, Pangasinan | 330025 | 2014-08-04 | 2014-09-24 |  | 330025 |  | Obligated
Construction of Perimeter Fence for Bani Police Station & Partition Wall @ 3rd floor of Bani PNP Bldg., | Poblacion, Bani, Pangasinan | 323994 | For Bidding |  |  |  |  | Obligated |  | 3917 | PR#5204
Fabrication/installation of Signages | 14 Hospitals around the Province | 905940 | On-going |  |  |  |  | Obligated |  | 3917 | PR#11860
Completion of 2-storey Multi-Purpose (Red Cross Bldg.) @ WPDH, Alaminos City |  | 664910 | 2013-09-05 | 2013-10-29 |  |  |  | Obligated |  | 3917 | PR#6347
Materials, labor, and other for construction of 1 unit exploratory/production deep well at NRSCC | (For Bidding) | 350000 | 8/5/204 | 2014-08-16 | 100% |  |  | Obligated
Construction of 2 units deepwell (D 180 ft) at Sitio Centro | Brgy. Mabini, Balungao, Pangasinan | 300000 | For Bidding |  |  |  |  | Obligated | 8919-2
Economic Development
Improvement (riprapping) of side slope | Brgy. Road, Brgy. Dupo, Binmaley, Pangasinan | 10332350.18 | 2014-04-12 | 2014-10-17 | 100% | 10332350.18 |  | Fully paid 10/2014 |  | CAD Const.PR# 1769 | 6911
Construction of roofing of 2 units pathway of Public Market | Bugallon, Pangasinan | 3250500.99 | 2014-05-12 | 2014-09-08 | 100% | 3250500.99 |  | Fully paid 11/2014 |  | Zota Trdg. PR# 1681
Repair/rehabilitation of Repair Bay No. 1 and Office Bldg., | Motorpool Compound, Lingayen, Pangasinan | 7301053.42 | 2014-06-05 | 2015-01-02 | 100% | 6566228.81 |  | Controlled 12-11-14 |  | Safeway Const. & Supply PR#1595
Construction of cattle shed at Bugallon Slaughter House | Socony, Bugallon, Pangasinan | 3240597 | 2014-11-30 | 2015-03-01 | 100% | 2103755.13 |  | Controlled 12-11-14 |  | Safeway Constn. PR#4066 | 6911
Repair/improvement of Slaughter House | Socony, Bugallon, Pangasinan | 1207909 | 2014-11-30 | 1/17/205 | 100% | 962929.56 |  | Controlled 12-11-14 |  | W.M. Salayog PR#10611 | 6911
Concreting of Quetegan-Bunlalacao Road | Mangatarem, Pangasinan | 7996775.42 | 2014-06-05 | 2015-12-12 | 100% | 7996775.42 |  | Paid 12-2014 |  | 8917-1 | Zota Trdg. PR# 1896
Concreting of Rajal-Esmeralda Road | Balungao, Pangasinan | 11250114.59 | 2014-11-21 | 2015-02-07 | 50% | 5619761.38 |  | Controlled 12-3-14 |  | 8917-1 | BET Constn PR# 2536
672 bags of Portland cement in concrete paving | Talibaew-Mankitkitao Road | 172518 | Materials Only |  | 100% | 172518 |  | Controlled 10-9-14 |  | 8917-1 | BET Const. PR#7172
14 drums E. Asphalt and 322.5 MT Pre-mix for Asphalting of Road Network | Urdaneta Dist. Hosp | 1973667.5 | 2014-12-04 | 2014-12-06 | 100% | 1973667.5 |  | Paid 12-2014 |  | 8917-1 | Oriental Sales PR#0337
Asphalt materials for Tibule St., Baloling | Mapandan, Pang | 362200 | 2014-04-10 | 2014-04-24 |  |  |  | Obligated |  | 8917-1 | PR#4106
300 bags cement Asphalt Sealant for Provincial Roads | Provincial Roads | 1334700 | [5 empty] | Obligated |  | 8917-1 | PR#10654
115 MT Asphalt Pre-Mix and 1 drum E. Asphalt for Improvement of Mangatarem | Manleluag Rd., Mangatarem, Pangasinan | 646900 | 2014-08-15 | 2014-08-15 |  |  |  | Obligated |  | 8917-1
Concreting of Sitio Joves Road | Brgy. Macabito, Calasiao, Pangasinan | 601124.13 | 2014-10-06 | 2014-10-16 | 100% | 601124.13 |  | Paid 12-2014 |  | 8917-1 | KJRS Constn. PR#11088
Asphalting Brgy., Dulag Road, | Binmaley, Pangasinan | 651040 | 2014-04-02 | 2014-04-02 | 100% | 651040 |  | Paid 12-2014 |  | 8917-1 | Oriental Sales PR#4156
Blocktopping of Brgy. Road, Brgy. Hacienda | Bugallon, Pangasinan | 1805530 | 2014-06-19 | 2014-06-20 | 100% | 1805530 |  | Paid 12-2014 |  | 8917-1 | Oriental Sales PR#
Additional works (Stone Masonry) for concreting of feeder Road | Brgy. Naguilayan, Binmaley, Pangasinan | 1817060 | For Bidding |  | 100% | 1817060 |  | Paid 12-2014 |  | 8917-1 | PR#5206
Asphalting of PSU Access Rd., | Bayambang, Pangasinan | 1669600 | 2014-07-23 | 2014-07-26 |  |  |  | Obligated |  | 8917-1 | PR#11047
Asphalt for blocktopping | Brgy. Bañaga, Bugallon | 541600 | 2014-11-07 | 2014-11-07 |  |  |  | Obligated |  | 8917-1 | PR#13001
Asphalting/blocktopping of Brgy. Canan Norte Road, Malasiqui, Pangasinan | Malasiqui, Pangasinan | 1831700 | 2014-11-14 | 2014-11-20 |  |  |  | Obligated |  | 8917-1 | PR#2941
Asphalting/blocktopping | Brgy.Naguelguel Rd., Lingayen | 2113500 | 2014-11-08 | 2014-11-13 |  |  |  | Obligated |  | 8917-1 | PR#13093
Asphalting/blocktopping various streets | Poblacion, Loac, Pangasinan | 1560900 | 2014-11-08 | 2014-11-14 |  |  |  | Obligated |  | 8917-1 | PR#1233
Asphalting of Alos-Quibuas Road | Alaminos, Pangasinan | 2455800 | 2014-11-08 | 2014-11-19 |  |  |  | Obligated |  | 8917-1 | PR#12321
Improvement/asphalting of Road Shoulder along Brgy. Buenlag and Macabito Rd., | Calasiao, Pangasinan | 596600 | 2014-11-08 | 2014-11-08 |  |  |  | Obligated |  | 8917-1 | PR#13097
200 bags cement for construction of Farm to Market Road of Brgy. San Gabriel St., | Bayambang, Pangasinan | 51900 |  |  | 100% | 51900 |  | Paid 11/2014 |  | 3917 | BET Constn PR#6603
Construction of Propagation Area & Irrigation/Drainage Canal, Phase II | Brgy. Tebag, Sta. Barbara, Pangasinan | 835759.14 | Not Yet Started |  |  |  |  | Obligated |  | 8919 | PR#10587
Payment of Loan Amortization | Land Bank of the Philippines | 129000000 |  |  |  | 129000000 |  | Paid as of December, 2014
Environmental Development
15500 pcs empty sacks of rice for preparation wasted disposal of dredging machine at Brgy. Dupo, Binmaley, Pangasinan | Sta. Barbara, San Quintin, Mangatarem and Lingayen | 185845 |  |  | 100% | 185845 |  | Paid in 11/2014 |  | 8912-4 | Anaw Trdg. PR#7334
Forest tree seeds, and other various materials needed for the propagation of fruit and forest tree seedlings at the field station | Sta. Barbara, San Quintin, Mangatarem and Lingayen | 299100 |  |  | 100% | 299100 |  | Paid 11/2014 |  | 8919 | Anaw Trdg., PR#7173
forest and fruit tree seedlings propagation at | OPAG-Field Stations | 221125 | [5 empty] | Obligated |  | 8919 | PR#13035
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO | [5 empty] | AMADO T. ESPINO, JR.
Provincial Accountant | [5 empty] | Governor

## SEF
FDP Form 11 - SEF Utilization
(SEF Budget Accountability Form No. 1)
REPORT OF SEF UTILIZATION
For the Quarter Ending December 31, 2014
Province/City Municipality |  | Pangasinan
Receipt from SEF |  |  |  | 162004699.87
Less: | DISBURSEMENTS (broken down by expense class and by object of expenditure)
Personal Services
-0-
Maintenance and Other Operating Expenses
55210813.71
Capital Outlay
-0-
Financial Expenses
-0-
Sub-total |  |  |  | 55210813.71
Balance |  |  |  | 106793886.16
We hereby certify that we have reviewed the
contents and hereby attest to the veracity and
correctness of the data or information
contained in this document.
ARTURO V. SORIANO
Provincial Accountant
AMADO T. ESPINO, JR.
Governor

## TRUST.FUND
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE OCTOBER - DECEMBER QUARTER, CY 2014
Province | : PANGASINAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Construction of Provincial Farmers' Multi-Purpose Center, Brgy. Gonzalo, San Quintin, Pangasinan | Brgy. Gonzalo, San Quintin, Pangasinan | 2995743.82 |  |  | 100% | 2995743.82 |  | fund from the Department of Agriculture
Delivery of 1,259 metric tons asphalt pre-mix and 38 drums emulsified asphalt for asphalt repair and ovelay along Rajal-Esmeralda Road, Balungao, Pangasinan | Rajal-Esmeralda Road, Balungao, Pangasinan | 7465215 |  |  |  | 7465215 |  | fund from the Department of Public Works and Highways-Special Local Road Fund (DPWH-SLRF)
52.35% delivery of 948.75 metric tons asphalt pre-mix and 29 drums emulsified asphalt for asphalt repair and overlay along Libsong-San Joaquin Road, Sta. Maria, Pangsinan | Libsong-san Joaquin Road, Sta. Maria, Pangasinan | 2947485 |  |  |  | 2947485 |  | fund from the Department of Public Works and Highways-Special Local Road Fund (DPWH-SLRF)
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO | [5 empty] | HON. AMADO T. ESPINO, JR.
Provincial Accountant | [5 empty] | Governor

## LDRRMC
FDP Form 8 - Local Disaster Risk Reduction and Management Fund Utilization
(COA Form)
LOCAL DISASTER RISK REDUCTION AND MANAGEMENT FUND UTILIZATION
For the Quarter OCTOBER - DECEMBER , CY 2014
Province of Pangasinan
| LDRRMF |  | NDRRMF
Particulars | Quick Response | Mitigation Fund |  | From Other LGUs | From Other Sources | Total
| Fund (QRF) | 70%
30%
A. Sources of Funds:
Current Appropriation | 38359696.5 | 90455958.5 |  |  |  | 128815655
Continuing Appropriation | [5 empty] | 0
Previous Year's Appropriation transferred to the Special Trust Fund |  | 17123836.17 |  |  |  | 17123836.17
Transfers/Grants | [5 empty] | 0
Others ( Please specify) | [5 empty] | 0
Total Funds Available | 38359696.5 | 107579794.67 | 0 | 0 | 0 | 145939491.17
B. Utilization
Medicines |  | 887198.6 |  |  |  | 887198.6
Medical Supplies | [5 empty] | 0
Food Supplies |  | 220919.5 |  |  |  | 220919.5
Office Supplies |  | 27091 |  |  |  | 27091
Repair of Evacuation Center | [5 empty] | 0
Institutional/Capacity Development ( Ex. Trainings, environmental assessment & other related activities) | [5 empty] | 0
Construction of Evacuation Center | [5 empty] | 0
Equipment | [5 empty] | 0
Transfer to other LGUs | [5 empty] | 0
Other Maintenance and Operating Expenses | 2160050 | 9337685.7 |  |  |  | 11497735.7
Traveling Expense |  | 162247 |  |  |  | 162247
Training Expense |  | 24562 |  |  |  | 24562
IT Equipment & Software |  | 190275 |  |  |  | 190275
Motor Vehicles |  | 4502120 |  |  |  | 4502120
Other Machineries and Equipment |  | 780000 |  |  |  | 780000
Other Property, Plant and Equipment |  | 2500000 |  |  |  | 2500000
Roads, Highways and Bridges |  | 22410100 |  |  |  | 22410100
Communication Equipment |  | 208588 |  |  |  | 208588
Gasoline, Oil, Lubricants |  | 107151.18 |  |  |  | 107151.18
Donations | [5 empty] | 0
Repair/Rehabilitation of Public Infrastructures, Roads, Highways and Bridges, etc. |  | 42211946 |  |  |  | 42211946
Repair & Maintenance-Motor Vehicles |  | 619113.5 |  |  |  | 619113.5
Total Utilization | 2160050 | 84188997.48 | 0 | 0 | 0 | 86349047.48
Unutilized Balance | 36199646.5 | 23390797.19 | 0 | 0 | 0 | 59590443.69
I hereby certify that I have reviewed the contents and hereby attest to the veracity and correctness of the data or
information containedin this document.
ARTURO V. SORIANO
Provincial Accountant

## UNLIQUIDATED.CASH.ADVANCES
FDP Form 12- Unliquidated Cash Advances
UNLIQUIDATED CASH ADVANCES
For the Year Ending December 31, 2014
Province, City or Municipality:
Name of Debtor (in alphabetical order) | Amount Balance | Date Granted | Purpose | Amount Due
|  |  |  | Current |  |  | Past Due
|  |  |  | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
Rommel Cardinoza | 0 | 2014-01-16
Cornel V. dela Cruz | 0 | 2014-01-16
Gerardo R. Santos | 0 | 2014-01-09
Aurora L. Bacay | 0 | 2014-01-09
Edwin B. Sison | 0 | 2014-01-08
Salvador Vedaña | 10000 | 2003-10-08 | Traveling Expenses | [5 empty] | 10000
Judge Dionisio C. Sison | 7000 | 2001-07-16 | [6 empty] | 7000
Eugenio G. Ramos | 2500 | 1999-04-14 | [6 empty] | 2500
Atty. Feliciano M. Bautista | 1200 | 1997-07-22 | Traveling Expenses | [5 empty] | 1200
BM Eduardo Perez, Sr. | 5000 | 1999-02-03 | Traveling Expenses | [5 empty] | 5000
BM Leonardo Caranto | 20000 | 1997-02-27 | Traveling Expenses | [5 empty] | 20000
BM Rogelio Law | 5000 | 1997-09-22 | Traveling Expenses | [5 empty] | 5000
Rodolfo M. Cortez | 20000 | 1996-06-20 | [6 empty] | 20000
Rodolfo M. Cortez | 30000 | 1997-04-10 | [6 empty] | 30000
Roderick Mina | 3600 | 1997-06-22 | Traveling Expenses | [5 empty] | 3600
Felipe Santillan | 1250 | 1978-02-28 | Traveling Expenses | [5 empty] | 1250
Narciso Ramos | 1250 | 1978-08-28 | Traveling Expenses | [5 empty] | 1250
Rodolfo Rodrigo | 500 | 1978-11-23 | Traveling Expenses | [5 empty] | 500
Rodolfo Itchon | 1000 | 1981-03-19 | Traveling Expenses | [5 empty] | 1000
Rodolfo Itchon | 1500 | 1982-05-07 | Traveling Expenses | [5 empty] | 1500
Rodolfo Rivera | 1300 | 1983-06-04 | Traveling Expenses | [5 empty] | 1300
Federico Victorio | 1500 | 1985-04-30 | Traveling Expenses | [5 empty] | 1500
Maximu Dulay | 5000 | 1989-06-16 | [6 empty] | 5000
Total | 117600 |  |  | 0 | 0 | 0 | 0 | 0 | 117600
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO |  |  |  |  | AMADO T. ESPINO, JR
Provincial Accountant |  |  |  |  | Governor

## STATEMENT OF CASHFLOWS
FDP Form 9 - Statement of Cash Flow
(COA Form)
PROVINCE OF PANGASINAN
STATEMENT OF CASH FLOWS
General Fund-100
For the Year Ended December 31, 2014
Cash Flows from Operating Activities:
Cash Inflows:
|  | Collection from Taxpayers | 141668687.25
|  | Share from Internal Revenue Collections | 2144832216
|  | Receipts from sale of goods or services | 456084830.08
|  | Interest Income | 2911640.13
|  | Other Receipts | 131432630.41
|  | Total Cash Inflow | 2876930003.87
Cash Outflows:
Payments to -
|  | To suppliers/creditors | 1215162287.36
|  | To employees | 903993471.38
|  | Interest Expenses | 37060124.89
|  | Other Disbursements | 194475
|  | Total Cash Outflow | 2156410358.63
| Cash Provided by (Used In) |  |  | 720519645.24
Cash Flows from Investing Activities:
Cash Inflows:
|  | Sale of Property, Plant and Equipment and Public | 38076.4
Sale of Debt Securities of other Entities
|  | Collection of Principal on Loans to other Entities | 6982575
|  | Total Cash Inflow | 7020651.4
Cash Outflows:
|  | Purchase of Property, Plant and Equipment and Public | 402494166.02
Infrastracture
Grant/Loans to Other Entities
|  | Total Cash Outflow | 402494166.02
| Cash Provided by (Used In) |  |  | -395473514.62
Cash Flows from Financing Activities:
Cash Inflows:
Issuance of Debt Securities
|  | Acquisition of Loan | 37624399.16
|  | Total Cash Inflow | 37624399.16
Cash Outflows:
Retirement/.Redemption of Debt Securities
|  | Payment of Loan Amortization | 138903342.06
|  | Total Cash Outflow | 138903342.06
| Cash Provided by (Used In) |  |  | -101278942.9
Net Increase in Cash |  |  |  | 223767187.72
Cash at Beginning of the Period- 1/31/2014 |  |  |  | 418325897.98
Cash at the End of the Period- 12/31/2014 |  |  |  | 642093085.7
Certified Correct:
ARTURO V. SORIANO, CPA
Provincial Accountant

## ANNUAL.DEBT.SERVICE
FDP Form 2 - Statement of Debt Service
(DBM-LBP Form No. 6)
ANNEX "F"
Republic of the Phillippines
Province of Pangasinan
General Fund
For the Year 2014
| Date |  | Principal | Previous Payment |  |  | Amount Due |  |  | Balance of the
Creditor | Contracted | Term | Amount |  | Made |  | (Budget Year) |  |  | Principal
|  |  |  | Principal | Interest | Total | Principal | Interest | Total
Land Bank of the | 2008-06-23 | 5 years | 343544988.37 | 343544988.37 | 88617084.83 | 432162073.2 | - | - | - | -
Philippines | 2008-08-19 | 7 years | 79249686 | 67928304 | 25835396.66 | 93763700.66 | 11321384 | 2066152.4 | 13387536.4 | 11321382
Dagupan Branch | 2009-12-11 | 10 years | 149942779.08 | 64797562 | 29418010.29 | 94215572.29 | 17029043.48 | 7748214.76 | 24777258.24 | 85145217.08
| 2010-05-14 | 7 years | 97255640 | 62521482.78 | 20822943.58 | 83344426.36 | 21893662.84 | 5607086.5 | 27500749.34 | 34734157.22
| 2010-02-19 | 5 years | 75437000 | 67365197.41 | 8054439.18 | 75419636.59 | 28503218.24 | 3390157.43 | 31893375.67 | 8071802.59
| 2009-12-17 | 10 years | 143108017.99 | 58318398.09 | 26261608.92 | 84580007.01 | 17689283.08 | 7961123.82 | 25650406.9 | 84789619.9
| 2010-06-28 | 8 years | 185854705 | 123902336 | 46272241.6 | 170174577.6 | 30975534 | 7898876.01 | 38874410.01 | 61952369
| 12//2012 | 10 years | 50228784.65 | 5580976.12 | 5403602.64 | 10984578.76 | 5603007.34 | 3529894.82 | 9132902.16 | 44647808.53
| 12//2012 | 10 years | 115955566.26 | 11744406.42 | 10036336.52 | 21780742.94 | 12008778.87 | 7565530.49 | 19574309.36 | 104211159.84
| 2014-03-28 | 10 years | 6922400 |  | 75150.26 |  |  |  |  | 6922400
| TOTAL |  | 1247499567.35 | 805703651.19 | 260796814.48 | 1066425315.41 | 145023911.85 | 45767036.23 | 190790948.08 | 441795916.16
We hereby certify that we have reviewed the contents and hereby attest to the veracity and
correctness of the data or information contained in this document.
ARTURO V. SORIANO | [7 empty] | AMADO T. ESPINO, JR.
Provincial Accountant | [7 empty] | Governor